## Cover Page
Test Automation Estimates
Test Automation Estimation
Controlled copy
C3 Protected
Controlled copy
C3 Protected
Controlled copy
C3 Protected
Controlled copy
C3 Protected

## Scope
Total No of Test cases | 500
Automation Test Suite - Scope
Complexity | Simple | Medium | Complex | Total
Number of Test Cases | 250 | 150 | 100 | 500
| Coverage | No of Test Case | Scope for automation
Account Payables | Invoice Creation
PO Matched
AP Payment
AP to GL
Core HR
My customer wants to implement account payables and their requirement is to have invoice creation and matched with 3-way PO. Their payment types are Check , EFT and Wire
RL Inputs
If total PD > 6 months | automation test Mgr
| Functional SME | 3 to 4 months
| Automation engineers | based on the PD's that is derived
<6 months
<3 months | Functional SME

## Overall Estimation
TEST AUTOMATION ESTIMATION - Regression
Effort Splitup
| Automation Activities | Activity Description | Estimated Hours Phase I |  |  | Minutes | KT
| KT / Automation Planning | Identification and Knowledge Transfer of test cases to the automation team | 70.8333 | Simple | 250 | 5 | 20.8333
|  |  |  | Medium | 150 | 10 | 25
|  |  |  | Complex | 100 | 15 | 25
[5 empty] | 500 | Total in hrs | 70.8333
| Test Automation Environment set up | Setting up of Test Automation Environment (Installation of Automation tool, Automation framework setup and getting access to Instance etc.) Integration with Test Mangement Tool | 56 | 7 Days
| Automation Design / Development | 1. Prepare Automation Test Plan 2. Develop/Redesign Reusable libraries for automation 4. Develop new automation scripts 5. Prepare Test data template(s) | 3616 | Simple | Medium | Complex | Automation Design
|  |  |  | 2 day | 1 day | 0.5 day
|  |  |  | 1.5 | 1 | 0.75 | No. Of test cases/day
|  |  |  | 1333.3333 | 1200 | 1066.6667
[5 empty] | Total in hrs | 3600
| Automation Execution (Dry Run) | 1. Prepare Test Data & Update the Test data's in the Excel Template(s) 2. Execution (dry run) of automation scripts | 571.4286 | Simple | Medium | Complex | Automation Execution
|  |  |  | 1 day | 1 day | 1 day
|  |  |  | 10 | 7 | 4 | No. Of test cases/day
|  |  |  | 200 | 171.4286 | 200
[5 empty] | Total in hrs | 571.4286
| Project Management | Project Management Activities | 215.7131
| Contingency | Contingency hours to make up for Application/Test tool non-availability | 226.4987
|  | Overall | 4756.4737
|  | Total Person Days | 594.5592
|  | Total Person Weeks | 118.9118
|  | Total Person Months | 29.728
|  | Estimated Resources (Automation Engineers) | 3
|  | Duration (in Weeks) | 39.6373 | 9.9093 | Months
Note on D12: Additional 16hrs for the preparation of Automation Test Plan

## Resourcing - Model (hidden)
i
Time Line - Automation Test Suite Development
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Anaylyze the Manual Test suite & KT on Existing Business Process
Test Automation tool & Environment set-up
Create Reusable Libraries
Design & Develop Automation Test Scripts
Dry Run of Automation Test scripts
Autmation Test suite Sign-Off & Preparation of User Guide
| Role (Onsite) | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
| Automation Test Manager (SM) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Senior Automation Tester (M) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Automation Tester (A) |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Automation Resourcing Total | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Functional SME/ BA (Onsite) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Functional Tester/BA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
` | Total | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Time Line - Regression Testing Support
Automation - Regression Test Support
Role
Automation Test Lead
Automation Tester
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
r