## Cover Page
TEST AUTOMATION ESTIMATE
ATS — Oracle Recruiting Cloud (ORC) · Option B: extend the existing automation framework
PROJECT DETAILS
Project Name | Oracle Recruiting Cloud (ORC) Implementation
Client / Org | Cognizant
Estimate For | Automation of the ATS ORC SIT/UAT regression suite
Test Lead | Tejal Dalavi
Delivery Approach | Extend the existing Selenium 4.40 + Cucumber 7.33 + TestNG + Allure framework
Framework Source | github.com/Vishnu-vardhan-401/erp-hcm-regression-testing
Scope Source | ATS_ORC_Test_Script_Register_20AUG26.xlsx (Fit/Gap V1.1)
Estimation Model | HGV_Automation Estimation_Uipath_V1.0.xlsx (activity structure)
Version | 1.0
Prepared By | Vishnu Vardhan G
Date | 24-Aug-2026
Status | Draft for review
ESTIMATE AT A GLANCE
Can the ATS ORC suite be automated? | Yes — see breakdown below
Total test scripts in register | 152 | scripts
In scope for automation | 144 | scripts
Recommended to stay manual | 8 | scripts
Complexity mix (Simple / Medium / Complex) | 34 / 89 / 21 | scripts
Total automation effort | 1105.468 | hours
Total effort in person days | 138.1835 | person days
Recommended team | Scenario A — 3 automation engineers + test manager + ORC SME
Indicative duration | 9.2122 | weeks
Indicative duration (months) | 2.3031 | months
Fastest option (Scenario C) | 4.3868 | weeks with 7 engineers
Effort saved vs UiPath option | 27.51% | lower effort
WORKBOOK CONTENTS
Scope | Script volumes, complexity mix, coverage by module, banding basis, and the scripts excluded from automation.
Complexity Basis | All 152 scripts with step count, personas, complexity score and band, in-scope flag and the drivers behind each rating.
Framework Reuse | What the existing framework already provides, what must be built, and the sizing of the ORC component library.
Overall Estimation | The effort model — KT, framework uplift, component library, scripting, dry run, PM and contingency, with a contingency sensitivity.
Resourcing Scenarios | Three team sizes and the duration each produces, with squad composition.
Resourcing Model | Phase plan by week and resource ramp by month for the recommended scenario.
Tool Comparison | UiPath Test Suite vs extending the existing framework — effort, duration, cost and risk side by side.
Assumptions & Risks | Basis of estimate, assumptions, exclusions and risks with mitigations.
CELL LEGEND
Input / assumption | Blue bold text on a yellow fill — editable lever. Change these to flex the estimate.
Calculated | Black text — driven by formulas. Do not overwrite.

## Scope
AUTOMATION SCOPE — ATS Oracle Recruiting Cloud (ORC)
Derived from ATS_ORC_Test_Script_Register_20AUG26.xlsx (152 scripts, Fit/Gap V1.1). Scope is identical to the UiPath estimate — only the delivery approach differs.
SCRIPT VOLUMES
| Total Test Scripts in Register | 152 | % of total
| In Scope for Automation | 144 | 94.74%
| Excluded — to remain manual | 8 | 5.263%
AUTOMATION TEST SUITE — SCOPE BY COMPLEXITY
| Complexity | Simple | Medium | Complex | Total | Feeds the "Overall Estimation" tab.
| Number of Test Scripts | 34 | 89 | 21 | 144
| % Mix | 23.61% | 61.81% | 14.58% | 100%
SCOPE BY MODULE (PROCESS)
| Module (Process) | Total Scripts | In Scope | Simple | Medium | Complex | Excluded
| Job Requisition | 32 | 30 | 10 | 18 | 2 | 2
| Job Offer | 26 | 26 | 3 | 18 | 5 | 0
| Candidate Selection Process | 25 | 25 | 3 | 18 | 4 | 0
| Employee Referral | 21 | 21 | 8 | 13 | 0 | 0
| Candidate Experience | 13 | 12 | 1 | 10 | 1 | 1
| Security | 9 | 9 | 6 | 3 | 0 | 0
| Integration | 9 | 9 | 2 | 1 | 6 | 0
| Interview Management | 9 | 9 | 0 | 6 | 3 | 0
| AI Agents | 3 | 0 | 0 | 0 | 0 | 3
| Reporting & Analytics | 3 | 3 | 1 | 2 | 0 | 0
| Recruiting Booster | 2 | 0 | 0 | 0 | 0 | 2
| Total | 152 | 144 | 34 | 89 | 21 | 8
COMPLEXITY BANDING BASIS (applied script-by-script on "Complexity Basis")
| Scoring drivers (+) | Test steps: 8–11 = +1, 12+ = +2 • Persona/login handoffs: 2 = +1, 3+ = +2 • Third-party integration (Talview, Mercer, PeopleSoft, background check, e-storage) = +3 • AI / non-deterministic output = +3 • Approval workflow = +1 • Email / notification / SMS = +1 • OTBI or report validation = +1 • Career-site / external candidate UI = +1 • File, resume or document handling = +1 • Bulk or mass action = +1
| Scoring drivers (−) | Pure configuration or field-visibility assertion (suppress / hidden / read-only / restricted / label) = −1
| Band thresholds | Score ≤ 1 = Simple • Score 2–4 = Medium • Score ≥ 5 = Complex
| Why this matters | The band drives both scripting and dry-run productivity rates on the "Overall Estimation" tab.
SCRIPTS EXCLUDED FROM AUTOMATION — recommended to remain manual
| Test Script ID | Module | Sub-Process | Reason for Exclusion
| TC01-JR | Job Requisition | AI Recruiting Assistant / Chatbot | AI-generated output is non-deterministic — no stable expected result to assert against. Validate manually / by sampling.
| TC018-JR | Job Requisition | Agency Posting Approval | Classified GAP in Fit/Gap V1.1 — only an interim manual workaround exists; no configured ORC behaviour to automate.
| TC012-CE | Candidate Experience | AI Agent Reuse | AI-generated output is non-deterministic — no stable expected result to assert against. Validate manually / by sampling.
| TC01-AI | AI Agents | AI Referral Matching | Classified GAP in Fit/Gap V1.1 — only an interim manual workaround exists; no configured ORC behaviour to automate.
| TC01-RB | Recruiting Booster | Targeted Campaigns | Delivery is via an external channel (SMS / campaign platform) outside the ORC UI — no automatable assertion point.
| TC02-RB | Recruiting Booster | SMS Communication | Classified GAP in Fit/Gap V1.1 — only an interim manual workaround exists; no configured ORC behaviour to automate.
| TC02-AI | AI Agents | Voice AI Agents | AI-generated output is non-deterministic — no stable expected result to assert against. Validate manually / by sampling.
| TC03-AI | AI Agents | AI in Candidate Selection Process | AI-generated output is non-deterministic — no stable expected result to assert against. Validate manually / by sampling.
Excluded scripts carry no automation build effort. They remain in the manual SIT/UAT pack.

## Complexity Basis
S.No | Test Script ID | Req ID | Module (Process) | Sub-Process | Priority | Classification | Test Type | No. of Test Steps | Personas Involved | Complexity Score | Complexity Band | In Scope for Automation | Automation Viability / Reason | Complexity Drivers
1 | TC01-REF | REQ_ERP_0001 | Employee Referral | Referral UI Configuration | Medium | FIT | Positive | 6 | 3 | 1 | Simple | Yes | Automate | 6 steps; 3 personas/2 logins; config/visibility assertion
2 | TC02-REF | REQ_ERP_0002 | Employee Referral | Referral Notifications | Low | FIT | Positive | 5 | 3 | 3 | Medium | Yes | Automate | 5 steps; 3 personas/1 logins; email/notification
3 | TC03-REF | REQ_ERP_0003 | Employee Referral | Job Search Configuration | Medium | FIT | Positive | 5 | 2 | 2 | Medium | Yes | Automate | 5 steps; 2 personas/1 logins; career-site/external UI
4 | TC04-REF | REQ_ERP_0003 | Employee Referral | Job Search Configuration | Medium | FIT | Negative | 6 | 1 | -1 | Simple | Yes | Automate | 6 steps; config/visibility assertion
5 | TC05-REF | REQ_ERP_0004 | Employee Referral | Referral Configuration Governance | Medium | FIT | Positive | 5 | 2 | 3 | Medium | Yes | Automate | 5 steps; 2 personas/1 logins; email/notification; career-site/external UI
6 | TC06-REF | REQ_ERP_0005 | Employee Referral | Duplicate Management | High | FIT | Positive | 10 | 2 | 4 | Medium | Yes | Automate | 10 steps; 2 personas/1 logins; email/notification; file/doc handling
7 | TC07-REF | REQ_ERP_0005 | Employee Referral | Duplicate Management | High | FIT | Negative | 8 | 1 | 2 | Medium | Yes | Automate | 8 steps; email/notification
8 | TC08-REF | REQ_ERP_0006 | Employee Referral | Resume Parsing (Referral Portal) | Medium | PARTIAL FIT | Positive | 10 | 1 | 2 | Medium | Yes | Automate | 10 steps; file/doc handling
9 | TC09-REF | REQ_ERP_0006 | Employee Referral | Resume Parsing (Referral Portal) | Medium | PARTIAL FIT | Negative | 8 | 1 | 2 | Medium | Yes | Automate | 8 steps; file/doc handling
10 | TC010-REF | REQ_ERP_0007 | Employee Referral | Referral Form Configuration | Low | FIT | Positive | 10 | 1 | 0 | Simple | Yes | Automate | 10 steps; config/visibility assertion
11 | TC011-REF | REQ_ERP_0008 | Employee Referral | Referral Consent Capture | High | FIT | Positive | 10 | 1 | 2 | Medium | Yes | Automate | 10 steps; email/notification
12 | TC012-REF | REQ_ERP_0008 | Employee Referral | Referral Consent Capture | High | FIT | Negative | 10 | 1 | 2 | Medium | Yes | Automate | 10 steps; email/notification
13 | TC013-REF | REQ_ERP_0009 | Employee Referral | Referrer Dashboard | Low | FIT | Positive | 8 | 2 | 3 | Medium | Yes | Automate | 8 steps; 2 personas/1 logins; report/OTBI
14 | TC014-REF | REQ_ERP_0010 | Employee Referral | Referral Reporting Access | Medium | FIT | Positive | 8 | 0 | 3 | Medium | Yes | Automate | 8 steps; 1 personas/2 logins; report/OTBI
15 | TC015-REF | REQ_ERP_0010 | Employee Referral | Referral Reporting Access | Medium | FIT | Negative | 8 | 0 | 1 | Simple | Yes | Automate | 8 steps; report/OTBI; config/visibility assertion
16 | TC016-REF | REQ_ERP_0011 | Employee Referral | Branding / Terminology | Low | FIT | Positive | 7 | 1 | -1 | Simple | Yes | Automate | 7 steps; config/visibility assertion
17 | TC017-REF | REQ_ERP_0012 | Employee Referral | Referral UI Configuration | Low | FIT | Positive | 8 | 2 | 1 | Simple | Yes | Automate | 8 steps; 2 personas/1 logins; config/visibility assertion
18 | TC018-REF | REQ_ERP_0012 | Employee Referral | Referral UI Configuration | Low | FIT | Negative | 9 | 1 | 1 | Simple | Yes | Automate | 9 steps; email/notification; config/visibility assertion
19 | TC019-REF | REQ_ERP_0013 | Employee Referral | Referral UI Configuration | Low | FIT | Positive | 7 | 1 | -1 | Simple | Yes | Automate | 7 steps; config/visibility assertion
20 | TC01-JR | REQ_JR_0001 | Job Requisition | AI Recruiting Assistant / Chatbot | Medium | FIT | Positive | 14 | 2 | 7 | Complex | No | Manual (AI/non-deterministic) | 14 steps; 2 personas/3 logins; AI/non-deterministic
21 | TC02-JR | REQ_JR_0002 | Job Requisition | Recruiting Activity Center | Medium | FIT | Positive | 10 | 1 | 2 | Medium | Yes | Automate | 10 steps; report/OTBI
22 | TC03-JR | REQ_JR_0002 | Job Requisition | Recruiting Activity Center | Medium | FIT | Negative | 9 | 1 | 0 | Simple | Yes | Automate | 9 steps; config/visibility assertion
23 | TC04-JR | REQ_JR_0003 | Job Requisition | Recruiting Activity Center | Medium | FIT | Positive | 10 | 1 | 2 | Medium | Yes | Automate | 10 steps; 1 personas/2 logins
24 | TC05-JR | REQ_JR_0004 | Job Requisition | Field-Level Compliance (Legal Name) | High | FIT | Positive | 15 | 1 | 5 | Complex | Yes | Automate (stub/mock 3rd party) | 15 steps; 3rd-party integration
25 | TC06-JR | REQ_JR_0004 | Job Requisition | Field-Level Compliance (Legal Name) | High | FIT | Negative | 8 | 1 | 1 | Simple | Yes | Automate | 8 steps
26 | TC07-JR | REQ_JR_0005 | Job Requisition | Role-Based Document Access | High | FIT | Positive | 13 | 3 | 4 | Medium | Yes | Automate | 13 steps; 3 personas/2 logins
27 | TC08-JR | REQ_JR_0005 | Job Requisition | Role-Based Document Access | High | FIT | Negative | 10 | 0 | 0 | Simple | Yes | Automate | 10 steps; config/visibility assertion
28 | TC09-JR | REQ_JR_0006 | Job Requisition | Requisition & Candidate Visibility (HM) | High | FIT | Positive | 10 | 2 | 2 | Medium | Yes | Automate | 10 steps; 2 personas/2 logins
29 | TC010-JR | REQ_JR_0007 | Job Requisition | Prescreening Question Governance | High | FIT | Positive | 11 | 1 | 0 | Simple | Yes | Automate | 11 steps; config/visibility assertion
30 | TC011-JR | REQ_JR_0007 | Job Requisition | Prescreening Question Governance | High | FIT | Negative | 9 | 1 | 3 | Medium | Yes | Automate | 9 steps; career-site/external UI; file/doc handling
31 | TC01-INTM | REQ_INTM_0001 | Interview Management | Interview Feedback Templates | Medium | FIT | Positive | 15 | 1 | 2 | Medium | Yes | Automate | 15 steps
32 | TC02-INTM | REQ_INTM_0002 | Interview Management | AI Interview Feedback Summary | Medium | PARTIAL FIT | Positive | 12 | 2 | 7 | Complex | Yes | Automate | 12 steps; 2 personas/3 logins; AI/non-deterministic
33 | TC03-INTM | REQ_INTM_0003 | Interview Management | Candidate Interview Survey | Medium | FIT | Positive | 13 | 1 | 5 | Complex | Yes | Automate | 13 steps; 1 personas/2 logins; email/notification; report/OTBI
34 | TC012-JR | REQ_JR_0008 | Job Requisition | Prescreening Question Timing | Medium | FIT | Positive | 6 | 1 | 0 | Simple | Yes | Automate | 6 steps
35 | TC013-JR | REQ_JR_0009 | Job Requisition | Candidate Status / Talent Pool | Medium | FIT | Positive | 11 | 1 | 2 | Medium | Yes | Automate | 11 steps; file/doc handling
36 | TC014-JR | REQ_JR_0010 | Job Requisition | Application Flow / Interview Questions | Medium | FIT | Positive | 11 | 1 | 2 | Medium | Yes | Automate | 11 steps; career-site/external UI
37 | TC015-JR | REQ_JR_0010 | Job Requisition | Application Flow / Interview Questions | Medium | FIT | Negative | 10 | 1 | 1 | Simple | Yes | Automate | 10 steps; career-site/external UI; config/visibility assertion
38 | TC01-JO | REQ_JO_0001 | Job Offer | Offer Field Configuration | Medium | FIT | Positive | 12 | 1 | 3 | Medium | Yes | Automate | 12 steps; file/doc handling
39 | TC016-JR | REQ_JR_0011 | Job Requisition | Requisition Types / Workflow Customization | Medium | FIT | Positive | 13 | 2 | 4 | Medium | Yes | Automate | 13 steps; 2 personas/1 logins; approval workflow
40 | TC017-JR | REQ_JR_0012 | Job Requisition | AI JD Creation & Reporting | Medium | FIT | Positive | 14 | 1 | 6 | Complex | Yes | Automate | 14 steps; AI/non-deterministic; report/OTBI
41 | TC018-JR | REQ_JR_0013 & REQ_JR_0015 | Job Requisition | Agency Posting Approval | Medium | GAP | Positive | 11 | 3 | 4 | Medium | No | Manual (GAP - workaround only) | 11 steps; 3 personas/2 logins; approval workflow
42 | TC019-JR | REQ_JR_0014 | Job Requisition | Confidential Job Posting | Medium | FIT | Positive | 14 | 1 | 3 | Medium | Yes | Automate | 14 steps; 1 personas/3 logins; config/visibility assertion
43 | TC020-JR | REQ_JR_0014 | Job Requisition | Confidential Job Posting | Medium | FIT | Negative | 8 | 0 | 1 | Simple | Yes | Automate | 8 steps; report/OTBI; config/visibility assertion
44 | TC04-INTM | REQ_INTM_0004 | Interview Management | Hybrid Interview Scheduling | Medium | FIT | Positive | 14 | 2 | 3 | Medium | Yes | Automate | 14 steps; 2 personas/1 logins
45 | TC05-INTM | REQ_INTM_0005 | Interview Management | Interview Scheduling Control | Medium | FIT | Positive | 13 | 2 | 3 | Medium | Yes | Automate | 13 steps; 2 personas/2 logins
46 | TC01-CE | REQ_CE-0002 | Candidate Experience | Career Site Branding | Low | FIT | Positive | 9 | 1 | 1 | Simple | Yes | Automate | 9 steps; career-site/external UI; config/visibility assertion
47 | TC01-INT | REQ_ING_0001 | Integration | Agency Usage Restrictions | Medium | FIT | Positive | 10 | 1 | 0 | Simple | Yes | Automate | 10 steps; config/visibility assertion
48 | TC02-INT | REQ_ING_0001 | Integration | Agency Usage Restrictions | Medium | FIT | Negative | 9 | 1 | 0 | Simple | Yes | Automate | 9 steps; config/visibility assertion
49 | TC06-INTM | REQ_INTM_0009 | Interview Management | Panel Profile Sharing | Medium | FIT | Positive | 12 | 2 | 5 | Complex | Yes | Automate | 12 steps; 2 personas/1 logins; email/notification; file/doc handling
50 | TC02-CE | REQ_CE-0003 | Candidate Experience | Talent Profile / Qualifications | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/3 logins
51 | TC02-JO | REQ_JO_0002 | Job Offer | Offer Letter Compliance (Job Description) | High | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; approval workflow
52 | TC03-JO | REQ_JO_0003 | Job Offer | Pay Transparency (Salary Range Display) | Critical | FIT | Positive | 10 | 2 | 3 | Medium | Yes | Automate | 10 steps; 2 personas/1 logins; career-site/external UI
53 | TC04-JO | REQ_JO_0004 | Job Offer | Compensation Automation | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
54 | TC05-JO | REQ_JO_0005 | Job Offer | Compensation / Salary Integration | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
55 | TC06-JO | REQ_JO_0006 | Job Offer | Offer Field Configuration | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
56 | TC021-JR | REQ_JR_0018 | Job Requisition | Job Posting Alerts | Low | FIT | Positive | 11 | 2 | 3 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins; report/OTBI
57 | TC07-INTM | REQ_INTM_0006 | Interview Management | Interview Reason Codes | Low | FIT | Positive | 13 | 1 | 2 | Medium | Yes | Automate | 13 steps
58 | TC07-JO | REQ_JO_0007 | Job Offer | Offer Compliance (COLA/Accommodation) | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
59 | TC08-JO | REQ_JO_0008 | Job Offer | Pay Transparency Compliance | Critical | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; career-site/external UI
60 | TC09-JO | REQ_JO_0009 | Job Offer | Compensation - HCM Integration | High | FIT | Positive | 12 | 1 | 5 | Complex | Yes | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration
61 | TC010-JO | REQ_JO_0010 | Job Offer | Compensation Configuration | Medium | PARTIAL FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
62 | TC011-JO | REQ_JO_0011 | Job Offer | Offer Compliance Fields | High | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
63 | TC012-JO | REQ_JO_0012 | Job Offer | Offer Compliance Validation | High | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
64 | TC013-JO | REQ_JO_0012 | Job Offer | Offer Compliance Validation | High | FIT | Negative | 10 | 1 | 1 | Simple | Yes | Automate | 10 steps
65 | TC03-INT | REQ_ING_0002 REQ_ING_0003 | Integration | Mercer Belong Integration | Medium | GAP | Positive | 6 | 1 | 3 | Medium | Yes | Automate (stub/mock 3rd party) | 6 steps; 3rd-party integration
66 | TC022-JR | REQ_JR_0016 | Job Requisition | Hire Type Classification | Medium | FIT | Positive | 11 | 1 | 1 | Simple | Yes | Automate | 11 steps
67 | TC014-JO | REQ_JO_0013 | Job Offer | Contract Workflow Configuration | Medium | FIT | Positive | 11 | 2 | 3 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins; approval workflow
68 | TC015-JO | REQ_JO_0014 | Job Offer | Pay Transparency Compliance | Critical | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; career-site/external UI
69 | TC016-JO | REQ_JO_0015 | Job Offer | Offer Approval Template | Medium | FIT | Positive | 11 | 2 | 4 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins; approval workflow; email/notification
70 | TC023-JR | REQ_JR_0017 | Job Requisition | Field-Level Visibility (Hiring Manager) | Medium | FIT | Positive | 11 | 1 | 1 | Simple | Yes | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
71 | TC024-JR | REQ_JR_0017 | Job Requisition | Field-Level Visibility (Hiring Manager) | Medium | FIT | Negative | 11 | 1 | 1 | Simple | Yes | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
72 | TC025-JR | REQ_JR_0019 | Job Requisition | Recruiter-HM Collaboration | Medium | FIT | Positive | 10 | 2 | 3 | Medium | Yes | Automate | 10 steps; 2 personas/2 logins; email/notification
73 | TC03-CE | REQ_CE_0004 | Candidate Experience | Application Flow (Easy Apply) | High | FIT | Positive | 13 | 2 | 5 | Complex | Yes | Automate | 13 steps; 2 personas/1 logins; career-site/external UI; file/doc handling
74 | TC04-CE | REQ_CE_0005 | Candidate Experience | Talent Community | Medium | FIT | Positive | 8 | 1 | 2 | Medium | Yes | Automate | 8 steps; email/notification; career-site/external UI; config/visibility assertion
75 | TC017-JO | REQ_JO_0016 | Job Offer | Offer Templates | Low | FIT | Positive | 10 | 2 | 3 | Medium | Yes | Automate | 10 steps; 2 personas/1 logins; file/doc handling
76 | TC01-CSP | REQ_CSP_0001 | Candidate Selection Process | Recruiter View Configuration | Medium | FIT | Positive | 11 | 3 | 3 | Medium | Yes | Automate | 11 steps; 3 personas/3 logins; career-site/external UI; config/visibility assertion
77 | TC02-CSP | REQ_CSP_0001 | Candidate Selection Process | Recruiter View Configuration | Medium | FIT | Negative | 10 | 2 | 2 | Medium | Yes | Automate | 10 steps; 2 personas/1 logins; career-site/external UI; config/visibility assertion
78 | TC05-CE | REQ_CE_0006 | Candidate Experience | Application Flow (Easy Apply v3) | Medium | FIT | Positive | 14 | 2 | 4 | Medium | Yes | Automate | 14 steps; 2 personas/1 logins; career-site/external UI; file/doc handling; config/visibility assertion
79 | TC06-CE | REQ_CE_0007 | Candidate Experience | Application Question Sets | High | FIT | Positive | 12 | 1 | 3 | Medium | Yes | Automate | 12 steps; career-site/external UI
80 | TC07-CE | REQ_CE_0008 | Candidate Experience | Country-Specific Application Flows | Medium | FIT | Positive | 11 | 2 | 3 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins; career-site/external UI
81 | TC08-CE | REQ_CE_0009 | Candidate Experience | Career Site Compliance Content | High | FIT | Positive | 9 | 1 | 2 | Medium | Yes | Automate | 9 steps; career-site/external UI
82 | TC09-CE | REQ_CE_0009 | Candidate Experience | Career Site Compliance Content | High | FIT | Negative | 10 | 1 | 2 | Medium | Yes | Automate | 10 steps; career-site/external UI
83 | TC03-CSP | REQ_CSP_0002 | Candidate Selection Process | Rehire Check Integration | Medium | FIT | Positive | 10 | 2 | 2 | Medium | Yes | Automate | 10 steps; 2 personas/1 logins
84 | TC020-REF | REQ_ERP_0014 | Employee Referral | Referral Consent / Compliance | High | FIT | Positive | 13 | 2 | 3 | Medium | Yes | Automate | 13 steps; 2 personas/1 logins
85 | TC021-REF | REQ_ERP_0014 | Employee Referral | Referral Consent / Compliance | High | FIT | Negative | 11 | 2 | 2 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins
86 | TC026-JR | REQ_JR_0020 | Job Requisition | Prescreening Question Template | High | FIT | Positive | 13 | 2 | 4 | Medium | Yes | Automate | 13 steps; 2 personas/1 logins; career-site/external UI
87 | TC027-JR | REQ_JR_0020 | Job Requisition | Prescreening Question Template | High | FIT | Negative | 12 | 1 | 3 | Medium | Yes | Automate | 12 steps; career-site/external UI
88 | TC028-JR | REQ_JR_0021 | Job Requisition | Requisition Status (Custom) | Low | FIT | Positive | 11 | 2 | 2 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins
89 | TC018-JO | REQ_JO_0017 | Job Offer | Offer Document Attachments | Medium | FIT | Positive | 12 | 2 | 5 | Complex | Yes | Automate | 12 steps; 2 personas/1 logins; email/notification; file/doc handling
90 | TC019-JO | REQ_JO_0018 | Job Offer | Compensation / Approval Matrix Automation | High | PARTIAL FIT | Positive | 12 | 2 | 5 | Complex | Yes | Automate | 12 steps; 2 personas/1 logins; approval workflow; file/doc handling
91 | TC020-JO | REQ_JO_0019 | Job Offer | Offer Fitment Form | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; approval workflow
92 | TC010-CE | REQ_CE_0010 | Candidate Experience | Candidate Profile Sharing | Medium | FIT | Positive | 12 | 3 | 4 | Medium | Yes | Automate | 12 steps; 3 personas/2 logins
93 | TC04-INT | REQ_ING_0004 | Integration | Talview Integration - Reporting | Medium | PARTIAL FIT | Positive | 11 | 2 | 6 | Complex | Yes | Automate (stub/mock 3rd party) | 11 steps; 2 personas/1 logins; 3rd-party integration; report/OTBI
94 | TC05-INT | REQ_ING_0005 | Integration | Talview Integration - Resume Flow | Medium | PARTIAL FIT | Positive | 12 | 1 | 7 | Complex | Yes | Automate (stub/mock 3rd party) | 12 steps; 1 personas/2 logins; 3rd-party integration; file/doc handling
95 | TC04-CSP | REQ_CSP_0003 | Candidate Selection Process | Candidate History Preservation | Medium | FIT | Positive | 11 | 1 | 2 | Medium | Yes | Automate | 11 steps; file/doc handling
96 | TC05-CSP | REQ_CSP_0004 | Candidate Selection Process | Bulk Candidate Search | Medium | FIT | Positive | 10 | 1 | 3 | Medium | Yes | Automate | 10 steps; email/notification; bulk/mass action
97 | TC06-CSP | REQ_CSP_0005 | Candidate Selection Process | Bulk Candidate Actions | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; bulk/mass action
98 | TC07-CSP | REQ_CSP_0006 | Candidate Selection Process | Candidate Status Labels | Medium | FIT | Positive | 12 | 2 | 2 | Medium | Yes | Automate | 12 steps; 2 personas/2 logins; config/visibility assertion
99 | TC021-JO | REQ_JO_0020 | Job Offer | Offer Phase States | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; approval workflow
100 | TC029-JR | REQ_JR_0022 | Job Requisition | System Status Labels | Medium | FIT | Positive | 11 | 3 | 3 | Medium | Yes | Automate | 11 steps; 3 personas/2 logins; report/OTBI; config/visibility assertion
101 | TC030-JR | REQ_JR_0022 | Job Requisition | System Status Labels | Medium | FIT | Negative | 10 | 3 | 2 | Medium | Yes | Automate | 10 steps; 3 personas/1 logins; config/visibility assertion
102 | TC08-CSP | REQ_CSP_0007 | Candidate Selection Process | Candidate Lifecycle Transfer | Medium | FIT | Positive | 12 | 1 | 3 | Medium | Yes | Automate | 12 steps; file/doc handling
103 | TC011-CE | REQ_CE_0011 | Candidate Experience | Career Site Import/Branding Reuse | Low | FIT | Positive | 12 | 2 | 3 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; career-site/external UI; config/visibility assertion
104 | TC012-CE | REQ_CE_0012 | Candidate Experience | AI Agent Reuse | Low | FIT | Positive | 12 | 2 | 7 | Complex | No | Manual (AI/non-deterministic) | 12 steps; 2 personas/1 logins; AI/non-deterministic; career-site/external UI
105 | TC06-INT | REQ_ING_0006 | Integration | Background Check Integration | High | FIT | Positive | 12 | 1 | 5 | Complex | Yes | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration
106 | TC09-CSP | REQ_CSP_0008 | Candidate Selection Process | Disposition Governance | Medium | FIT | Positive | 12 | 3 | 3 | Medium | Yes | Automate | 12 steps; 3 personas/4 logins; config/visibility assertion
107 | TC010-CSP | REQ_CSP_0008 | Candidate Selection Process | Disposition Governance | Medium | FIT | Negative | 11 | 1 | 0 | Simple | Yes | Automate | 11 steps; config/visibility assertion
108 | TC011-CSP | REQ_CSP_0009 | Candidate Selection Process | Recruiter vs HM Ownership | Medium | FIT | Positive | 12 | 3 | 3 | Medium | Yes | Automate | 12 steps; 3 personas/3 logins; config/visibility assertion
109 | TC012-CSP | REQ_CSP_0009 | Candidate Selection Process | Recruiter vs HM Ownership | Medium | FIT | Negative | 12 | 2 | 2 | Medium | Yes | Automate | 12 steps; 2 personas/2 logins; config/visibility assertion
110 | TC013-CSP | REQ_CSP_0010 | Candidate Selection Process | AI - JD to Questions | Medium | PARTIAL FIT | Positive | 11 | 1 | 2 | Medium | Yes | Automate | 11 steps; file/doc handling
111 | TC014-CSP | REQ_CSP_0011 | Candidate Selection Process | Contextualization Rules | Medium | FIT | Positive | 11 | 2 | 3 | Medium | Yes | Automate | 11 steps; 2 personas/1 logins; career-site/external UI
112 | TC015-CSP | REQ_CSP_0012 | Candidate Selection Process | Job Codes / Prescreening Updates | Medium | FIT | Positive | 12 | 3 | 5 | Complex | Yes | Automate | 12 steps; 3 personas/2 logins; career-site/external UI
113 | TC08-INTM | REQ_INTM_0007 | Interview Management | Candidate/HM Survey Framework | Medium | FIT | Positive | 12 | 2 | 3 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins
114 | TC09-INTM | REQ_INTM_0008 | Interview Management | Survey Reporting | Medium | PARTIAL FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; report/OTBI
115 | TC031-JR | REQ_JR_0023 | Job Requisition | Agency Onboarding Governance | Medium | FIT | Positive | 10 | 4 | 4 | Medium | Yes | Automate | 10 steps; 4 personas/1 logins; approval workflow
116 | TC016-CSP | REQ_CSP_0013 | Candidate Selection Process | Duplicate Check Checkpoints | High | FIT | Positive | 12 | 2 | 3 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins
117 | TC017-CSP | REQ_CSP_0013 | Candidate Selection Process | Duplicate Check Checkpoints | High | FIT | Negative | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; email/notification
118 | TC018-CSP | REQ_CSP_0014 | Candidate Selection Process | Duplicate Match Logic | High | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Automate | 12 steps; 2 personas/1 logins; email/notification
119 | TC019-CSP | REQ_CSP_0015 | Candidate Selection Process | Source Ownership Logic | High | FIT | Positive | 12 | 3 | 5 | Complex | Yes | Automate | 12 steps; 3 personas/1 logins; career-site/external UI
120 | TC020-CSP | REQ_CSP_0016 | Candidate Selection Process | Source Edit Access Control | Medium | FIT | Positive | 11 | 2 | 2 | Medium | Yes | Automate | 11 steps; 2 personas/2 logins
121 | TC021-CSP | REQ_CSP_0016 | Candidate Selection Process | Source Edit Access Control | Medium | FIT | Negative | 11 | 2 | 1 | Simple | Yes | Automate | 11 steps; 2 personas/1 logins; config/visibility assertion
122 | TC022-CSP | REQ_CSP_0017 | Candidate Selection Process | Source Taxonomy | Medium | PARTIAL FIT | Positive | 13 | 1 | 4 | Medium | Yes | Automate | 13 steps; email/notification; report/OTBI
123 | TC01-SEC | REQ_SEC_0001 | Security | Agency View Restriction | Medium | FIT | Positive | 10 | 2 | 1 | Simple | Yes | Automate | 10 steps; 2 personas/2 logins; config/visibility assertion
124 | TC02-SEC | REQ_SEC_0001 | Security | Agency View Restriction | Medium | FIT | Negative | 10 | 3 | 2 | Medium | Yes | Automate | 10 steps; 3 personas/2 logins; config/visibility assertion
125 | TC023-CSP | REQ_CSP_0018 | Candidate Selection Process | Source Ownership Retention | Medium | FIT | Positive | 11 | 2 | 1 | Simple | Yes | Automate | 11 steps; 2 personas/1 logins; config/visibility assertion
126 | TC01-AI | REQ_AI_0001 | AI Agents | AI Referral Matching | Medium | GAP | Positive | 11 | 2 | 4 | Medium | No | Manual (GAP - workaround only) | 11 steps; 2 personas/1 logins; career-site/external UI; file/doc handling
127 | TC07-INT | REQ_ING_0007 | Integration | Document Storage Integration | Medium | PARTIAL FIT | Positive | 12 | 1 | 6 | Complex | Yes | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration; file/doc handling
128 | TC08-INT | REQ_ING_0008 | Integration | Onboarding-PeopleSoft Integration | High | PARTIAL FIT | Positive | 13 | 2 | 6 | Complex | Yes | Automate (stub/mock 3rd party) | 13 steps; 2 personas/1 logins; 3rd-party integration
129 | TC09-INT | REQ_ING_0009 | Integration | Document Records - eStorage | Medium | PARTIAL FIT | Positive | 12 | 1 | 6 | Complex | Yes | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration; file/doc handling
130 | TC013-CE | REQ_CE_0013 | Candidate Experience | Duplicate/Prior Application Visibility | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Automate | 12 steps
131 | TC03-SEC | REQ_SEC_0002 | Security | Country/Team Access Restriction | High | FIT | Positive | 11 | 0 | 1 | Simple | Yes | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
132 | TC04-SEC | REQ_SEC_0002 | Security | Country/Team Access Restriction | High | FIT | Negative | 11 | 2 | 1 | Simple | Yes | Automate | 11 steps; 2 personas/1 logins; config/visibility assertion
133 | TC01-RB | REQ_RB_0001 | Recruiting Booster | Targeted Campaigns | Medium | PARTIAL FIT | Positive | 12 | 1 | 3 | Medium | No | Manual (external channel) | 12 steps; email/notification
134 | TC024-CSP | REQ_CSP_0019 | Candidate Selection Process | Campus & Event Management | Medium | FIT | Positive | 12 | 2 | 7 | Complex | Yes | Automate | 12 steps; 2 personas/1 logins; 3rd-party integration; bulk/mass action
135 | TC02-RB | REQ_RB_0002 | Recruiting Booster | SMS Communication | Medium | GAP | Positive | 11 | 1 | 5 | Complex | No | Manual (GAP - workaround only) | 11 steps; 3rd-party integration; email/notification
136 | TC022-JO | REQ_JO_0021 | Job Offer | Salary Data Restriction | High | FIT | Positive | 11 | 0 | 1 | Simple | Yes | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
137 | TC023-JO | REQ_JO_0021 | Job Offer | Salary Data Restriction | High | FIT | Negative | 6 | 1 | -1 | Simple | Yes | Automate | 6 steps; config/visibility assertion
138 | TC01-REP | REQ_REP_0001 | Reporting & Analytics | Real-Time Metrics Dashboard | Medium | FIT | Positive | 6 | 2 | 2 | Medium | Yes | Automate | 6 steps; 2 personas/1 logins; report/OTBI
139 | TC02-AI | REQ_AI_0002 | AI Agents | Voice AI Agents | Medium | GAP | Positive | 6 | 2 | 4 | Medium | No | Manual (AI/non-deterministic) | 6 steps; 2 personas/1 logins; AI/non-deterministic
140 | TC032-JR | REQ_JR_0025 | Job Requisition | Recruiter-Owned Process Governance | Medium | FIT | Positive | 6 | 4 | 2 | Medium | Yes | Automate | 6 steps; 4 personas/3 logins
141 | TC05-SEC | REQ_SEC_0003 | Security | Interview/Selection/Offer Visibility | High | FIT | Positive | 6 | 2 | 1 | Simple | Yes | Automate | 6 steps; 2 personas/3 logins; config/visibility assertion
142 | TC03-AI | REQ_AI_0003 | AI Agents | AI in Candidate Selection Process | Medium | FIT | Positive | 6 | 3 | 2 | Medium | No | Manual (AI/non-deterministic) | 6 steps; 3 personas/1 logins
143 | TC02-REP | REQ_REP_0002 | Reporting & Analytics | Admin/MIS Report Restriction | Medium | FIT | Positive | 6 | 1 | 2 | Medium | Yes | Automate | 6 steps; 1 personas/3 logins; report/OTBI; config/visibility assertion
144 | TC03-REP | REQ_REP_0002 | Reporting & Analytics | Admin/MIS Report Restriction | Medium | FIT | Negative | 6 | 2 | 1 | Simple | Yes | Automate | 6 steps; 2 personas/1 logins; report/OTBI; config/visibility assertion
145 | TC06-SEC | REQ_SEC_0004 | Security | Role-Based Recruiter Assignment | High | FIT | Positive | 6 | 2 | 1 | Simple | Yes | Automate | 6 steps; 2 personas/1 logins
146 | TC07-SEC | REQ_SEC_0005 | Security | US Collaborator/Recruiter Restrictions | High | FIT | Positive | 6 | 2 | 1 | Simple | Yes | Automate | 6 steps; 2 personas/5 logins; config/visibility assertion
147 | TC08-SEC | REQ_SEC_0005 | Security | US Collaborator/Recruiter Restrictions | High | FIT | Positive | 12 | 3 | 4 | Medium | Yes | Automate | 12 steps; 3 personas/2 logins; approval workflow; config/visibility assertion
148 | TC09-SEC | REQ_SEC_0006 | Security | US Collaborator Offer Restriction | High | FIT | Negative | 12 | 2 | 3 | Medium | Yes | Automate | 12 steps; 2 personas/3 logins; config/visibility assertion
149 | TC024-JO | REQ_JO_0022 | Job Offer | Offer Proposal / Dynamic Approvals / Contract Generation | High | FIT | Positive | 13 | 4 | 6 | Complex | Yes | Automate | 13 steps; 4 personas/2 logins; approval workflow; file/doc handling
150 | TC025-JO | REQ_JO_0023 | Job Offer | Offer Document Library / Mandatory Attachments | High | FIT | Positive | 12 | 3 | 5 | Complex | Yes | Automate | 12 steps; 3 personas/1 logins; file/doc handling
151 | TC026-JO | REQ_JO_0024 | Job Offer | Offer Letter Compliance / Job Description & Designation | High | FIT | Positive | 12 | 1 | 3 | Medium | Yes | Automate | 12 steps; report/OTBI
152 | TC025-CSP | REQ_CSP_0020 | Candidate Selection Process | Rehire Employee ID Capture / Flow | High | FIT | Positive | 9 | 2 | 5 | Complex | Yes | Automate | 9 steps; 2 personas/1 logins; email/notification; report/OTBI; career-site/external UI

## Framework Reuse
EXISTING FRAMEWORK — what carries over to ORC, and what must be built
Source: github.com/Vishnu-vardhan-401/erp-hcm-regression-testing. This tab is the evidence behind the lower environment set-up and script-development effort in this estimate.
ASSETS ALREADY BUILT (reused for ORC)
Asset | What it does | Size | Reuse for ORC
Selenium + Cucumber + TestNG + Allure stack | Selenium 4.40, Cucumber 7.33, TestNG, Allure 2.29, Apache POI — already on a current, supported toolchain. | pom.xml | Direct
Wrapper.java | 30+ reusable interaction methods: waits, JS click, scroll, highlight, Oracle date picker, custom oj- dropdown select, screenshot capture, Allure pass/fail reporting. | 454 lines | Direct
redwoodSync() | Redwood/JET page-settle helper already in place — the Redwood UI is a solved problem in this framework, not a new risk. | In Wrapper | Direct (harden)
HCMCoreHR.java | Mature Oracle Fusion page object — 685 locators, overwhelmingly Redwood/JET component-based (oj-select-single ×111, oj-input-text, oj-input-date, oj-switch, oj-table, oj-list-view). | 9,055 lines | Pattern + locator strategy
HCMSecurity.java + TileValidationReportUtil | Generic role/tile visibility validator driven from Excel, with HTML result tables in Allure. | 682 + 295 lines | Direct — maps to the 9 ORC Security scripts
ExcelReader + Excel-driven runner | Key-based Excel lookup plus ExcelDrivenCucumberRunner / ExcelFeaturePicker — test selection and data both driven from a spreadsheet the test team can edit. | 95 + 420 lines | Direct
AllureReportUtil + Hooks | Screenshot-on-failure, text/HTML/CSV/PNG attachments, scenario tagging and context. | 83 + 39 lines | Direct
Delivered scenarios | 56 Core HR + 27 Security scenarios already automated and reported against an Oracle Fusion pod. | 83 scenarios | Proof of throughput
Total framework code in repo | Across page objects, step definitions, utilities, hooks and runners. | 13,314 lines
GAPS TO CLOSE (this is what the "Framework Uplift & Environment Set-up" line pays for)
Gap | Why it matters for ORC | Fix
Single static WebDriver in BaseClass | No parallel execution. With 144 scripts and multi-persona flows, serial runs make every regression cycle long. | Refactor to a ThreadLocal driver.
driver.quit() after every scenario (Hooks) | A fresh browser and a fresh Oracle login per scenario — the slowest part of each run. | Session reuse per persona where the test allows.
redwoodSync() uses a fixed 4-second sleep | A hard 4s wait on every call inflates runtime across 144 scripts. | Replace with a condition-based wait.
Hardcoded Windows chromedriver paths | Will not run on a Linux CI agent. | Selenium Manager / WebDriverManager.
No ORC/Recruitment page objects | PageObjectManagerHCM has the Recruitment page object commented out — ORC screens do not exist yet. | Covered by the component library build below.
testng.xml is a stub; no CI pipeline in repo | No scheduled or triggered execution. | Suite definition plus a CI job.
COMPONENT / PAGE OBJECT LIBRARY BUILD
Hours per new component |  | 7 | Locator discovery on Redwood/JET, page-object methods and stabilisation. Single biggest lever on this tab.
| Functional Area | Components Required | Reuse from Existing Framework | Net New Components | Hours
| Common / shared (login, navigation, search, dropdowns, dates, upload, notifications, approvals) | 8 | 85% | 1.2 | 8.4
| Job Requisition (create/edit, posting, prescreening, activity centre, approvals, status) | 7 | 10% | 6.3 | 44.1
| Job Offer (offer create, fields, compensation, approvals, letter & documents, phases) | 7 | 10% | 6.3 | 44.1
| Candidate Selection Process (search, profile, disposition, duplicate check, sources, bulk) | 6 | 10% | 5.4 | 37.8
| Employee Referral portal (referral form, job search, dashboard, consent, notifications) | 5 | 10% | 4.5 | 31.5
| Candidate Experience / career site (easy apply, talent community, question sets, branding) | 5 | 5% | 4.75 | 33.25
| Interview Management (scheduling, feedback templates, panel, surveys) | 4 | 10% | 3.6 | 25.2
| Security (role / tile visibility) | 3 | 80% | 0.6 | 4.2
| Reporting & Analytics (OTBI) | 2 | 25% | 1.5 | 10.5
| Integration boundary / stubs | 3 | 10% | 2.7 | 18.9
| Total | 50 |  | 36.85 | 257.95
Reuse % basis: | Common and Security are high because Wrapper, BaseClass, ExcelReader, AllureReportUtil, HCMSecurity and TileValidationReportUtil already deliver that behaviour against Oracle Fusion. The ORC transaction screens (requisition, candidate, offer, referral portal, career site) do not exist in the framework and are costed as new, with a small credit for shared UI patterns.

## Overall Estimation
TEST AUTOMATION ESTIMATION — ATS Oracle Recruiting Cloud (ORC)
Approach: extend the existing Selenium 4.40 + Cucumber + TestNG + Allure framework ¦ Scope identical to the UiPath estimate ¦ Blue/shaded cells are inputs.
Effort Splitup
| Automation Activities | Activity Description | Estimated Hours (Phase I) | Complexity | No. of Scripts | Rate | Basis
| KT / Automation Planning | Identification and knowledge transfer of the ORC test scripts to the automation team; walkthrough of Fit/Gap V1.1 and the recruiting business processes. Tool-independent — unchanged from the UiPath estimate. | 22.9167 | Simple | 34 | 5 | 2.8333 | Minutes per script
|  |  |  | Medium | 89 | 10 | 14.8333
|  |  |  | Complex | 21 | 15 | 5.25
[5 empty] | 144 | Total in hrs | 22.9167
| Framework Uplift & Environment Set-up | ThreadLocal driver refactor for parallel execution, session reuse in Hooks, condition-based redwoodSync, Selenium Manager for cross-platform drivers, ORC pod configuration and test-user wiring, TestNG suite definition and CI pipeline. No tool licensing or install — the framework already exists. | 32 | 4 Days |  |  |  | vs 56 hrs on UiPath
| Component / Page Object Library Build | One-time build of the ORC page objects and reusable components, net of what the existing framework already provides. Sized area by area on the "Framework Reuse" tab. | 257.95 | From "Framework Reuse"
| Automation Script Development | 1. Prepare Automation Test Plan 2. Write feature files and step definitions per test script 3. Prepare test data template(s) Rates assume the component library above is in place, so scripting is assembly of existing page-object methods. | 544.5587 | Simple | Medium | Complex
|  |  |  | 0.29 | 0.44 | 0.8 | Days per script
|  |  |  | 3.5 | 2.25 | 1.25 | No. of scripts / day
|  |  |  | 77.7143 | 316.4444 | 134.4 | Hours
[5 empty] | Total in hrs | 528.5587 | Test Plan & Data Templates (hrs) | 16
| Automation Execution (Dry Run) | 1. Prepare test data and populate the Excel test data template(s) 2. Dry-run execution, defect triage and script stabilisation. Rates assume parallel execution is available after the framework uplift. | 145.2667 | Simple | Medium | Complex
|  |  |  | 0.08 | 0.13 | 0.2 | Days per script
|  |  |  | 12 | 8 | 5 | No. of scripts / day
|  |  |  | 22.6667 | 89 | 33.6 | Hours
[5 empty] | Total in hrs | 145.2667
| Project Management | Automation test management, planning, status reporting, governance and stakeholder co-ordination. | 50.1346 | 5% | of build effort
| Contingency | Contingency for environment non-availability, ORC quarterly update impact and rework. Held at 5% for comparability — see the sensitivity block below. | 52.6413 | 5% | of effort incl. PM
|  | Overall Effort (Hours) | 1105.468
|  | Total Person Days | 138.1835 | 1 person day = 8 hrs
|  | Total Person Weeks | 27.6367 | 1 person week = 5 days
|  | Total Person Months | 6.9092 | 1 month = 4 weeks (per source model)
|  | Estimated Resources (Automation Engineers) | 3 | Flex this cell, or see "Resourcing Scenarios"
|  | Duration (in Weeks) | 9.2122 | 2.3031 | Months
CONTINGENCY SENSITIVITY
|  | Contingency % | Overall Effort (Hours) | Person Weeks | Duration @ 3 engineers (weeks)
|  | 5% | 1105.468 | 27.6367 | 9.2122 | Comparable with the UiPath estimate.
|  | 8% | 1137.0528 | 28.4263 | 9.4754 | Reflects a code-based framework carrying its own locator maintenance.
|  | 12% | 1179.1659 | 29.4791 | 9.8264 | Prudent if ORC configuration is still moving during the build.

## Resourcing Scenarios
RESOURCING SCENARIOS — effort is fixed, only elapsed time changes
Total effort from the "Overall Estimation" tab is constant across all three scenarios. Adding engineers compresses the calendar but costs more in co-ordination, which the efficiency factor reflects.
SQUAD COMPOSITION
Role | Scenario A Lean | Scenario B Balanced | Scenario C Accelerated | Counts as automation engineer?
Automation Test Manager | 0.5 | 1 | 1 | No
Senior Automation Tester (Java/Selenium) | 1 | 2 | 2 | Yes
Automation Tester (Java/Selenium) | 2 | 3 | 5 | Yes
Functional SME / BA (ORC) | 1 | 1 | 2 | No
Automation Engineers (build capacity) | 3 | 5 | 7 | Senior + Testers
Total Squad Size | 4.5 | 7 | 10
DURATION BY SCENARIO
Scenario | Automation Engineers | Team Efficiency Factor | Effective Capacity (FTE) | Computed Duration (Weeks) | Planned Duration (Weeks) | Planned Duration (Months) | Guidance
A — Lean (Recommended) | 3 | 100% | 3 | 9.2122 | 9.2122 | 2.3031 | Mirrors the 3-engineer default. The component library is the critical path — one senior engineer owning it keeps the page objects consistent.
B — Balanced | 5 | 95% | 4.75 | 5.8183 | 5.8183 | 1.4546 | Use when the SIT/UAT window is tight. Split the component library by module across two seniors, with a shared locator convention agreed up front.
C — Accelerated | 7 | 90% | 6.3 | 4.3868 | 4.3868 | 1.0967 | Only viable if the component library is complete before the extra testers join — five people writing page objects in parallel will duplicate locators.
Total effort (person weeks) — constant | 27.6367 | Effort does not fall as the team grows; only elapsed time does.
Serial floor (weeks) | 3.5 | Framework uplift, KT and final sign-off cannot be parallelised. Lower than the UiPath floor because no tool install or Orchestrator setup is needed.

## Resourcing Model
DELIVERY TIMELINE — Scenario A (Lean: 3 automation engineers, ~10 weeks)
Indicative phasing. Weeks are relative to automation kick-off, not calendar dates.
PHASE PLAN
Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Analyse manual test suite & KT on ORC business processes
Framework uplift (ThreadLocal, Selenium Manager, CI, ORC config)
Build ORC component / page object library
Write feature files & step definitions
Dry run of automation scripts
Defect triage & script stabilisation
Suite sign-off & user guide
RESOURCE RAMP (headcount by month, 1 month = 4 weeks)
Role | Month 1 | Month 2 | Month 3
Automation Test Manager | 0.5 | 0.5 | 0.5
Senior Automation Tester (Java/Selenium) | 1 | 1 | 1
Automation Tester (Java/Selenium) | 1 | 2 | 2
Functional SME / BA (ORC) | 1 | 1 | 0.5
Total | 3.5 | 4.5 | 4
Note: the senior engineer owns the component library end to end so locator conventions stay consistent. The Functional SME steps down once script design is signed off.

## Tool Comparison
TOOL COMPARISON — UiPath Test Suite vs extending the existing framework
UiPath figures are carried across from ATS_ORC_Automation_Estimation_UiPath_V1.0.xlsx and are entered as constants (blue). Selenium figures are live formulas from this workbook. Both cover the same 144 in-scope scripts.
QUANTITATIVE
Measure | UiPath Test Suite | Extend Existing Framework | Difference
Overall effort (hours) | 1524.94 | 1105.468 | -419.472
Total person days | 190.62 | 138.1835 | -52.4365
Total person weeks | 38.12 | 27.6367 | -10.4833
Environment / framework set-up (hours) | 56 | 32 | -24
Duration @ 3 engineers (weeks) | 12.71 | 9.2122 | -3.4978
Duration @ 5 engineers (weeks) | 8.03 | 5.8183 | -2.2117
Effort per in-scope script (hours) | 10.5899 | 7.6769 | -2.913
Saving vs UiPath |  | 27.51% | lower effort
QUALITATIVE
Dimension | UiPath Test Suite | Extend Existing Framework
Tool licence cost | Per-seat Studio and Test Manager plus Orchestrator. Not costed in either estimate — add it here. | Nil. Open-source stack already in use.
Reusable assets on day 1 | None specific to ORC. Object repository built from scratch. | 13,314 lines of framework code, 685 Redwood-aware locators, 30+ wrapper methods, Excel data layer, Allure reporting.
Proven on Oracle Fusion? | Vendor-supported, but unproven in this team. | Yes — 83 scenarios already delivered against an Oracle Fusion pod.
Redwood / JET handling | Vendor-maintained Oracle selectors. | redwoodSync() plus oj-component locator strategy already proven on Core HR.
Skills required | UiPath Studio. Lower barrier, easier to staff from outside the team. | Java, Selenium, Cucumber. The team already has this; harder to backfill.
Parallel execution | Orchestrator, out of the box. | Needs the ThreadLocal refactor — included in the 32-hour uplift.
CI/CD | Orchestrator scheduling and dashboards. | Maven + TestNG on any standard CI. Pipeline not yet in the repo.
Maintenance model | Vendor absorbs some UI change; licence renews annually. | Team owns every locator. Cheaper to run, but the burden is real and needs funding.
Vendor support | Yes, with SLAs. | Community only.
Principal risk | Licence cost and lock-in; a second asset base to maintain alongside the existing one. | Maintenance capacity. If the team that owns the framework moves on, the suite decays.
Read this as: | Extending the framework is cheaper and faster because the hard part — a Redwood-aware Oracle Fusion automation layer — already exists and is proven. The trade is that all maintenance sits with your team. UiPath buys vendor support and easier staffing, at licence cost and with no reuse of what is already built.

## Assumptions & Risks
ASSUMPTIONS, EXCLUSIONS & RISKS
BASIS OF ESTIMATE
| Scope source | ATS_ORC_Test_Script_Register_20AUG26.xlsx — 152 test scripts derived from ATS - ORC - Fit/Gap V1.1, prepared by Tejal Dalavi, 17-Aug-2026.
| Estimation model | Activity structure from HGV_Automation Estimation_Uipath_V1.0.xlsx, with the build split into a one-time component library plus per-script scripting — the accurate shape for a code-based framework.
| Delivery approach | Extend the existing Selenium 4.40 + Cucumber 7.33 + TestNG + Allure framework (github.com/Vishnu-vardhan-401/erp-hcm-regression-testing).
| What changed from the UiPath estimate | Environment set-up 56 → 32 hrs, a separately sized component library net of existing reuse, and faster per-script rates once page objects exist. KT, scope and complexity banding are unchanged.
ASSUMPTIONS
1 | The existing framework repository is available to the ORC team, and the engineers who built it are available for handover.
2 | A working ORC test instance is available for the full duration, with stable configuration and no mid-build re-implementation of recruiting flows.
3 | Test users are provisioned up front for every persona in the register — Recruiter, Hiring Manager, Employee/Referrer, Candidate, Interviewer, Agency and Administrator — with passwords that do not expire during the engagement.
4 | The 152 scripts are baselined before automation begins. The register itself notes that test steps, preconditions, test data and expected results are still to be edited and reviewed.
5 | Component-library rates assume the page objects follow the existing convention (contains(@id, ...) on oj- components) rather than positional XPath.
6 | Per-script rates assume the relevant page objects exist before scripting starts for that module — hence the phase overlap on the "Resourcing Model" tab.
7 | Engineers are already skilled in Java, Selenium and Cucumber. No tool training is included.
8 | One person day = 8 hours, one person week = 5 days, one month = 4 weeks.
9 | Effort covers build and dry run only (Phase I). Regression execution cycles after handover are estimated separately.
10 | Third-party integration scripts (Talview, Mercer Belong, PeopleSoft, background check, e-storage) are automated against stubs or a vendor sandbox; if neither is available these 9 scripts move to manual.
EXCLUSIONS
1 | Performance, load, security-penetration and accessibility testing.
2 | Manual SIT/UAT execution effort, and the 8 scripts listed as excluded on the "Scope" tab.
3 | Infrastructure, CI runner and browser-grid hosting costs.
4 | Test management tool licences and configuration.
5 | Post-handover regression execution and maintenance for Oracle quarterly updates.
6 | Retrofitting the Core HR and Security suites onto the uplifted framework.
7 | Automation of ORC configuration/setup itself (Setup and Maintenance tasks).
RISKS
| Risk | Impact if it materialises | Mitigation
| Test scripts are not yet baselined — the register flags steps, data and expected results as still to be reviewed. | Rework of built scripts; the largest single threat to the estimate. | Gate the build on a signed-off script; sequence modules so stable ones are automated first.
| All locator maintenance sits with the team — no vendor absorbs Oracle UI change. | Suite decays across the four Oracle quarterly updates a year if maintenance is unfunded. | Fund a maintenance retainer at handover; run against each Oracle update preview environment; keep locators centralised in page objects.
| Component library is the critical path — scripting cannot start on a module until its page objects exist. | Adding testers early produces idle capacity or duplicated locators. | One senior engineer owns the library; stagger module starts as the phase plan shows.
| Key-person dependency on the engineers who built the existing framework. | Reuse assumptions collapse; effort trends back toward a from-scratch build. | Book handover time explicitly; document the locator convention and wrapper API before build starts.
| redwoodSync() currently uses a fixed 4-second sleep, and a browser is launched per scenario. | Dry run and every later regression cycle run far slower than they need to. | Included in the 32-hour uplift: condition-based waits, ThreadLocal driver, session reuse.
| Third-party integration sandboxes (Talview, Mercer Belong, PeopleSoft, background check) may be unavailable. | 9 Complex scripts cannot be automated end to end; coverage drops. | Confirm sandbox availability before build; otherwise stub the boundary and assert only ORC-side behaviour.
| Test users and role provisioning delayed across the recruiting personas. | Blocks build and dry run — most scripts need two or more personas. | Raise provisioning as a week-1 dependency with named owners.