## Cover Page
TEST AUTOMATION ESTIMATE
ATS — Oracle Recruiting Cloud (ORC) ¦ Phase 1: 11 Countries
PROJECT DETAILS
Project Name | Oracle Recruiting Cloud (ORC) Implementation
Client / Org | Cognizant
Phase | Phase 1 — 11 of 81 countries
Test Lead | Tejal Dalavi
Automation Approach | Selenium WebDriver + Cucumber BDD (existing in-house framework, extended)
Scope Source | ATS_ORC_Test_Script_Register_20AUG26.xlsx (Fit/Gap V1.1)
Version | 2.0
Prepared By | Vishnu Vardhan G
Date | 24-Aug-2026
Status | Draft for review
ESTIMATE AT A GLANCE
Can the ORC suite be automated? | Yes — 144 of 152 scripts
Total test scripts in register | 152 | scripts
In scope for automation | 144 | scripts
Remain manual | 8 | scripts
Country-variant scripts | 27 | of which
Countries in Phase 1 | 11 | of 81
Script-executions to dry-run | 414 | executions
Total effort | 2605.5196 | hours
Total effort in person days | 325.6899 | person days
Duration — 3 engineers | 21.7127 | weeks
Duration — 4 engineers | 16.7881 | weeks
Duration — 5 engineers | 13.8591 | weeks
WORKBOOK CONTENTS
Scope | Phase 1 country coverage, script volumes, complexity mix, country-variant split, executions, module coverage and exclusions.
Complexity Basis | All 152 scripts with complexity band, in-scope flag, country-variant flag and the drivers behind each rating.
Overall Estimation | The effort model — analysis, framework extension, script development, country parameterisation, dry run, PM and contingency.
Resourcing Scenarios | 3, 4 and 5 engineer options with durations, squad composition and an indicative phase plan.
Assumptions & Risks | Basis of estimate, assumptions, exclusions and risks with mitigations.
CELL LEGEND
Input / assumption | Blue bold on yellow — editable. Change country count, rates or team mix here.
Calculated | Formula-driven. Do not overwrite.

## Scope
AUTOMATION SCOPE — ATS Oracle Recruiting Cloud (ORC), Phase 1
Derived from ATS_ORC_Test_Script_Register_20AUG26.xlsx (152 scripts, Fit/Gap V1.1). Automation approach: Selenium WebDriver with Cucumber BDD, extending the team's existing Oracle Fusion regression framework.
PHASE 1 COVERAGE
| Countries in Phase 1 | 11 | of | 81 | total in programme scope |  | Change cell D6 to re-estimate a later phase (e.g. 81 for full rollout). Everything recalculates.
| Phase 1 share of country scope | 13.58%
SCRIPT VOLUMES
| Total Test Scripts in Register | 152 | % of total
| In Scope for Automation | 144 | 94.74%
| Excluded — remain manual | 8 | 5.263%
SCOPE BY COMPLEXITY (in-scope scripts)
| Script Group | Simple | Medium | Complex | Total |  | Country-variant scripts carry country-specific behaviour — pay transparency, offer compliance, application flows, legal-name rules, country access restrictions.
| Country-variant — run once per country | 6 | 17 | 4 | 27
| Global — run once only | 28 | 72 | 17 | 117
| All in-scope scripts | 34 | 89 | 21 | 144
| % Mix | 23.61% | 61.81% | 14.58%
SCRIPT EXECUTIONS IN PHASE 1
| Execution Group | Simple | Medium | Complex | Total
| Global scripts × 1 run | 28 | 72 | 17 | 117 |  | This is the number that grows with countries, not the build. More countries add data rows and execution passes, not new scripts.
| Country-variant scripts × Phase 1 countries | 66 | 187 | 44 | 297
| Total script-executions to dry-run | 94 | 259 | 61 | 414
SCOPE BY MODULE (PROCESS)
| Module (Process) | Total Scripts | In Scope | Country-Variant | Simple | Medium | Complex
| Job Requisition | 32 | 30 | 3 | 10 | 18 | 2
| Job Offer | 26 | 26 | 12 | 3 | 18 | 5
| Candidate Selection Process | 25 | 25 | 2 | 3 | 18 | 4
| Employee Referral | 21 | 21 | 0 | 8 | 13 | 0
| Candidate Experience | 13 | 12 | 5 | 1 | 10 | 1
| Interview Management | 9 | 9 | 1 | 0 | 6 | 3
| Security | 9 | 9 | 4 | 6 | 3 | 0
| Integration | 9 | 9 | 0 | 2 | 1 | 6
| AI Agents | 3 | 0 | 0 | 0 | 0 | 0
| Reporting & Analytics | 3 | 3 | 0 | 1 | 2 | 0
| Recruiting Booster | 2 | 0 | 0 | 0 | 0 | 0
| Total | 152 | 144 | 27 | 34 | 89 | 21
SCRIPTS EXCLUDED FROM AUTOMATION
| Test Script ID | Module | Sub-Process | Reason
| TC01-JR | Job Requisition | AI Recruiting Assistant / Chatbot | AI-generated output is non-deterministic — no stable expected result to assert against.
| TC018-JR | Job Requisition | Agency Posting Approval | Classified GAP in Fit/Gap V1.1 — only an interim manual workaround exists.
| TC012-CE | Candidate Experience | AI Agent Reuse | AI-generated output is non-deterministic — no stable expected result to assert against.
| TC01-AI | AI Agents | AI Referral Matching | Classified GAP in Fit/Gap V1.1 — only an interim manual workaround exists.
| TC01-RB | Recruiting Booster | Targeted Campaigns | Delivered via an external channel (SMS / campaign platform) outside the ORC UI.
| TC02-RB | Recruiting Booster | SMS Communication | Classified GAP in Fit/Gap V1.1 — only an interim manual workaround exists.
| TC02-AI | AI Agents | Voice AI Agents | AI-generated output is non-deterministic — no stable expected result to assert against.
| TC03-AI | AI Agents | AI in Candidate Selection Process | AI-generated output is non-deterministic — no stable expected result to assert against.

## Complexity Basis
S.No | Test Script ID | Req ID | Module (Process) | Sub-Process | Priority | Classification | Test Type | No. of Test Steps | Personas Involved | Complexity Score | Complexity Band | In Scope for Automation | Country-Variant | Automation Viability / Reason | Complexity Drivers
1 | TC01-REF | REQ_ERP_0001 | Employee Referral | Referral UI Configuration | Medium | FIT | Positive | 6 | 3 | 1 | Simple | Yes | No | Automate | 6 steps; 3 personas/2 logins; config/visibility assertion
2 | TC02-REF | REQ_ERP_0002 | Employee Referral | Referral Notifications | Low | FIT | Positive | 5 | 3 | 3 | Medium | Yes | No | Automate | 5 steps; 3 personas/1 logins; email/notification
3 | TC03-REF | REQ_ERP_0003 | Employee Referral | Job Search Configuration | Medium | FIT | Positive | 5 | 2 | 2 | Medium | Yes | No | Automate | 5 steps; 2 personas/1 logins; career-site/external UI
4 | TC04-REF | REQ_ERP_0003 | Employee Referral | Job Search Configuration | Medium | FIT | Negative | 6 | 1 | -1 | Simple | Yes | No | Automate | 6 steps; config/visibility assertion
5 | TC05-REF | REQ_ERP_0004 | Employee Referral | Referral Configuration Governance | Medium | FIT | Positive | 5 | 2 | 3 | Medium | Yes | No | Automate | 5 steps; 2 personas/1 logins; email/notification; career-site/external UI
6 | TC06-REF | REQ_ERP_0005 | Employee Referral | Duplicate Management | High | FIT | Positive | 10 | 2 | 4 | Medium | Yes | No | Automate | 10 steps; 2 personas/1 logins; email/notification; file/doc handling
7 | TC07-REF | REQ_ERP_0005 | Employee Referral | Duplicate Management | High | FIT | Negative | 8 | 1 | 2 | Medium | Yes | No | Automate | 8 steps; email/notification
8 | TC08-REF | REQ_ERP_0006 | Employee Referral | Resume Parsing (Referral Portal) | Medium | PARTIAL FIT | Positive | 10 | 1 | 2 | Medium | Yes | No | Automate | 10 steps; file/doc handling
9 | TC09-REF | REQ_ERP_0006 | Employee Referral | Resume Parsing (Referral Portal) | Medium | PARTIAL FIT | Negative | 8 | 1 | 2 | Medium | Yes | No | Automate | 8 steps; file/doc handling
10 | TC010-REF | REQ_ERP_0007 | Employee Referral | Referral Form Configuration | Low | FIT | Positive | 10 | 1 | 0 | Simple | Yes | No | Automate | 10 steps; config/visibility assertion
11 | TC011-REF | REQ_ERP_0008 | Employee Referral | Referral Consent Capture | High | FIT | Positive | 10 | 1 | 2 | Medium | Yes | No | Automate | 10 steps; email/notification
12 | TC012-REF | REQ_ERP_0008 | Employee Referral | Referral Consent Capture | High | FIT | Negative | 10 | 1 | 2 | Medium | Yes | No | Automate | 10 steps; email/notification
13 | TC013-REF | REQ_ERP_0009 | Employee Referral | Referrer Dashboard | Low | FIT | Positive | 8 | 2 | 3 | Medium | Yes | No | Automate | 8 steps; 2 personas/1 logins; report/OTBI
14 | TC014-REF | REQ_ERP_0010 | Employee Referral | Referral Reporting Access | Medium | FIT | Positive | 8 | 0 | 3 | Medium | Yes | No | Automate | 8 steps; 1 personas/2 logins; report/OTBI
15 | TC015-REF | REQ_ERP_0010 | Employee Referral | Referral Reporting Access | Medium | FIT | Negative | 8 | 0 | 1 | Simple | Yes | No | Automate | 8 steps; report/OTBI; config/visibility assertion
16 | TC016-REF | REQ_ERP_0011 | Employee Referral | Branding / Terminology | Low | FIT | Positive | 7 | 1 | -1 | Simple | Yes | No | Automate | 7 steps; config/visibility assertion
17 | TC017-REF | REQ_ERP_0012 | Employee Referral | Referral UI Configuration | Low | FIT | Positive | 8 | 2 | 1 | Simple | Yes | No | Automate | 8 steps; 2 personas/1 logins; config/visibility assertion
18 | TC018-REF | REQ_ERP_0012 | Employee Referral | Referral UI Configuration | Low | FIT | Negative | 9 | 1 | 1 | Simple | Yes | No | Automate | 9 steps; email/notification; config/visibility assertion
19 | TC019-REF | REQ_ERP_0013 | Employee Referral | Referral UI Configuration | Low | FIT | Positive | 7 | 1 | -1 | Simple | Yes | No | Automate | 7 steps; config/visibility assertion
20 | TC01-JR | REQ_JR_0001 | Job Requisition | AI Recruiting Assistant / Chatbot | Medium | FIT | Positive | 14 | 2 | 7 | Complex | No | No | Manual (AI/non-deterministic) | 14 steps; 2 personas/3 logins; AI/non-deterministic
21 | TC02-JR | REQ_JR_0002 | Job Requisition | Recruiting Activity Center | Medium | FIT | Positive | 10 | 1 | 2 | Medium | Yes | No | Automate | 10 steps; report/OTBI
22 | TC03-JR | REQ_JR_0002 | Job Requisition | Recruiting Activity Center | Medium | FIT | Negative | 9 | 1 | 0 | Simple | Yes | No | Automate | 9 steps; config/visibility assertion
23 | TC04-JR | REQ_JR_0003 | Job Requisition | Recruiting Activity Center | Medium | FIT | Positive | 10 | 1 | 2 | Medium | Yes | No | Automate | 10 steps; 1 personas/2 logins
24 | TC05-JR | REQ_JR_0004 | Job Requisition | Field-Level Compliance (Legal Name) | High | FIT | Positive | 15 | 1 | 5 | Complex | Yes | Yes | Automate (stub/mock 3rd party) | 15 steps; 3rd-party integration
25 | TC06-JR | REQ_JR_0004 | Job Requisition | Field-Level Compliance (Legal Name) | High | FIT | Negative | 8 | 1 | 1 | Simple | Yes | Yes | Automate | 8 steps
26 | TC07-JR | REQ_JR_0005 | Job Requisition | Role-Based Document Access | High | FIT | Positive | 13 | 3 | 4 | Medium | Yes | No | Automate | 13 steps; 3 personas/2 logins
27 | TC08-JR | REQ_JR_0005 | Job Requisition | Role-Based Document Access | High | FIT | Negative | 10 | 0 | 0 | Simple | Yes | No | Automate | 10 steps; config/visibility assertion
28 | TC09-JR | REQ_JR_0006 | Job Requisition | Requisition & Candidate Visibility (HM) | High | FIT | Positive | 10 | 2 | 2 | Medium | Yes | No | Automate | 10 steps; 2 personas/2 logins
29 | TC010-JR | REQ_JR_0007 | Job Requisition | Prescreening Question Governance | High | FIT | Positive | 11 | 1 | 0 | Simple | Yes | No | Automate | 11 steps; config/visibility assertion
30 | TC011-JR | REQ_JR_0007 | Job Requisition | Prescreening Question Governance | High | FIT | Negative | 9 | 1 | 3 | Medium | Yes | No | Automate | 9 steps; career-site/external UI; file/doc handling
31 | TC01-INTM | REQ_INTM_0001 | Interview Management | Interview Feedback Templates | Medium | FIT | Positive | 15 | 1 | 2 | Medium | Yes | Yes | Automate | 15 steps
32 | TC02-INTM | REQ_INTM_0002 | Interview Management | AI Interview Feedback Summary | Medium | PARTIAL FIT | Positive | 12 | 2 | 7 | Complex | Yes | No | Automate | 12 steps; 2 personas/3 logins; AI/non-deterministic
33 | TC03-INTM | REQ_INTM_0003 | Interview Management | Candidate Interview Survey | Medium | FIT | Positive | 13 | 1 | 5 | Complex | Yes | No | Automate | 13 steps; 1 personas/2 logins; email/notification; report/OTBI
34 | TC012-JR | REQ_JR_0008 | Job Requisition | Prescreening Question Timing | Medium | FIT | Positive | 6 | 1 | 0 | Simple | Yes | No | Automate | 6 steps
35 | TC013-JR | REQ_JR_0009 | Job Requisition | Candidate Status / Talent Pool | Medium | FIT | Positive | 11 | 1 | 2 | Medium | Yes | No | Automate | 11 steps; file/doc handling
36 | TC014-JR | REQ_JR_0010 | Job Requisition | Application Flow / Interview Questions | Medium | FIT | Positive | 11 | 1 | 2 | Medium | Yes | No | Automate | 11 steps; career-site/external UI
37 | TC015-JR | REQ_JR_0010 | Job Requisition | Application Flow / Interview Questions | Medium | FIT | Negative | 10 | 1 | 1 | Simple | Yes | No | Automate | 10 steps; career-site/external UI; config/visibility assertion
38 | TC01-JO | REQ_JO_0001 | Job Offer | Offer Field Configuration | Medium | FIT | Positive | 12 | 1 | 3 | Medium | Yes | No | Automate | 12 steps; file/doc handling
39 | TC016-JR | REQ_JR_0011 | Job Requisition | Requisition Types / Workflow Customization | Medium | FIT | Positive | 13 | 2 | 4 | Medium | Yes | No | Automate | 13 steps; 2 personas/1 logins; approval workflow
40 | TC017-JR | REQ_JR_0012 | Job Requisition | AI JD Creation & Reporting | Medium | FIT | Positive | 14 | 1 | 6 | Complex | Yes | No | Automate | 14 steps; AI/non-deterministic; report/OTBI
41 | TC018-JR | REQ_JR_0013 & REQ_JR_0015 | Job Requisition | Agency Posting Approval | Medium | GAP | Positive | 11 | 3 | 4 | Medium | No | No | Manual (GAP - workaround only) | 11 steps; 3 personas/2 logins; approval workflow
42 | TC019-JR | REQ_JR_0014 | Job Requisition | Confidential Job Posting | Medium | FIT | Positive | 14 | 1 | 3 | Medium | Yes | No | Automate | 14 steps; 1 personas/3 logins; config/visibility assertion
43 | TC020-JR | REQ_JR_0014 | Job Requisition | Confidential Job Posting | Medium | FIT | Negative | 8 | 0 | 1 | Simple | Yes | No | Automate | 8 steps; report/OTBI; config/visibility assertion
44 | TC04-INTM | REQ_INTM_0004 | Interview Management | Hybrid Interview Scheduling | Medium | FIT | Positive | 14 | 2 | 3 | Medium | Yes | No | Automate | 14 steps; 2 personas/1 logins
45 | TC05-INTM | REQ_INTM_0005 | Interview Management | Interview Scheduling Control | Medium | FIT | Positive | 13 | 2 | 3 | Medium | Yes | No | Automate | 13 steps; 2 personas/2 logins
46 | TC01-CE | REQ_CE-0002 | Candidate Experience | Career Site Branding | Low | FIT | Positive | 9 | 1 | 1 | Simple | Yes | No | Automate | 9 steps; career-site/external UI; config/visibility assertion
47 | TC01-INT | REQ_ING_0001 | Integration | Agency Usage Restrictions | Medium | FIT | Positive | 10 | 1 | 0 | Simple | Yes | No | Automate | 10 steps; config/visibility assertion
48 | TC02-INT | REQ_ING_0001 | Integration | Agency Usage Restrictions | Medium | FIT | Negative | 9 | 1 | 0 | Simple | Yes | No | Automate | 9 steps; config/visibility assertion
49 | TC06-INTM | REQ_INTM_0009 | Interview Management | Panel Profile Sharing | Medium | FIT | Positive | 12 | 2 | 5 | Complex | Yes | No | Automate | 12 steps; 2 personas/1 logins; email/notification; file/doc handling
50 | TC02-CE | REQ_CE-0003 | Candidate Experience | Talent Profile / Qualifications | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/3 logins
51 | TC02-JO | REQ_JO_0002 | Job Offer | Offer Letter Compliance (Job Description) | High | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Yes | Automate | 12 steps; 2 personas/1 logins; approval workflow
52 | TC03-JO | REQ_JO_0003 | Job Offer | Pay Transparency (Salary Range Display) | Critical | FIT | Positive | 10 | 2 | 3 | Medium | Yes | Yes | Automate | 10 steps; 2 personas/1 logins; career-site/external UI
53 | TC04-JO | REQ_JO_0004 | Job Offer | Compensation Automation | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Yes | Automate | 12 steps
54 | TC05-JO | REQ_JO_0005 | Job Offer | Compensation / Salary Integration | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | No | Automate | 12 steps
55 | TC06-JO | REQ_JO_0006 | Job Offer | Offer Field Configuration | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Yes | Automate | 12 steps
56 | TC021-JR | REQ_JR_0018 | Job Requisition | Job Posting Alerts | Low | FIT | Positive | 11 | 2 | 3 | Medium | Yes | No | Automate | 11 steps; 2 personas/1 logins; report/OTBI
57 | TC07-INTM | REQ_INTM_0006 | Interview Management | Interview Reason Codes | Low | FIT | Positive | 13 | 1 | 2 | Medium | Yes | No | Automate | 13 steps
58 | TC07-JO | REQ_JO_0007 | Job Offer | Offer Compliance (COLA/Accommodation) | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Yes | Automate | 12 steps
59 | TC08-JO | REQ_JO_0008 | Job Offer | Pay Transparency Compliance | Critical | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Yes | Automate | 12 steps; 2 personas/1 logins; career-site/external UI
60 | TC09-JO | REQ_JO_0009 | Job Offer | Compensation - HCM Integration | High | FIT | Positive | 12 | 1 | 5 | Complex | Yes | Yes | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration
61 | TC010-JO | REQ_JO_0010 | Job Offer | Compensation Configuration | Medium | PARTIAL FIT | Positive | 12 | 1 | 2 | Medium | Yes | No | Automate | 12 steps
62 | TC011-JO | REQ_JO_0011 | Job Offer | Offer Compliance Fields | High | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Yes | Automate | 12 steps
63 | TC012-JO | REQ_JO_0012 | Job Offer | Offer Compliance Validation | High | FIT | Positive | 12 | 1 | 2 | Medium | Yes | Yes | Automate | 12 steps
64 | TC013-JO | REQ_JO_0012 | Job Offer | Offer Compliance Validation | High | FIT | Negative | 10 | 1 | 1 | Simple | Yes | Yes | Automate | 10 steps
65 | TC03-INT | REQ_ING_0002 REQ_ING_0003 | Integration | Mercer Belong Integration | Medium | GAP | Positive | 6 | 1 | 3 | Medium | Yes | No | Automate (stub/mock 3rd party) | 6 steps; 3rd-party integration
66 | TC022-JR | REQ_JR_0016 | Job Requisition | Hire Type Classification | Medium | FIT | Positive | 11 | 1 | 1 | Simple | Yes | Yes | Automate | 11 steps
67 | TC014-JO | REQ_JO_0013 | Job Offer | Contract Workflow Configuration | Medium | FIT | Positive | 11 | 2 | 3 | Medium | Yes | No | Automate | 11 steps; 2 personas/1 logins; approval workflow
68 | TC015-JO | REQ_JO_0014 | Job Offer | Pay Transparency Compliance | Critical | FIT | Positive | 12 | 2 | 4 | Medium | Yes | Yes | Automate | 12 steps; 2 personas/1 logins; career-site/external UI
69 | TC016-JO | REQ_JO_0015 | Job Offer | Offer Approval Template | Medium | FIT | Positive | 11 | 2 | 4 | Medium | Yes | No | Automate | 11 steps; 2 personas/1 logins; approval workflow; email/notification
70 | TC023-JR | REQ_JR_0017 | Job Requisition | Field-Level Visibility (Hiring Manager) | Medium | FIT | Positive | 11 | 1 | 1 | Simple | Yes | No | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
71 | TC024-JR | REQ_JR_0017 | Job Requisition | Field-Level Visibility (Hiring Manager) | Medium | FIT | Negative | 11 | 1 | 1 | Simple | Yes | No | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
72 | TC025-JR | REQ_JR_0019 | Job Requisition | Recruiter-HM Collaboration | Medium | FIT | Positive | 10 | 2 | 3 | Medium | Yes | No | Automate | 10 steps; 2 personas/2 logins; email/notification
73 | TC03-CE | REQ_CE_0004 | Candidate Experience | Application Flow (Easy Apply) | High | FIT | Positive | 13 | 2 | 5 | Complex | Yes | Yes | Automate | 13 steps; 2 personas/1 logins; career-site/external UI; file/doc handling
74 | TC04-CE | REQ_CE_0005 | Candidate Experience | Talent Community | Medium | FIT | Positive | 8 | 1 | 2 | Medium | Yes | No | Automate | 8 steps; email/notification; career-site/external UI; config/visibility assertion
75 | TC017-JO | REQ_JO_0016 | Job Offer | Offer Templates | Low | FIT | Positive | 10 | 2 | 3 | Medium | Yes | No | Automate | 10 steps; 2 personas/1 logins; file/doc handling
76 | TC01-CSP | REQ_CSP_0001 | Candidate Selection Process | Recruiter View Configuration | Medium | FIT | Positive | 11 | 3 | 3 | Medium | Yes | No | Automate | 11 steps; 3 personas/3 logins; career-site/external UI; config/visibility assertion
77 | TC02-CSP | REQ_CSP_0001 | Candidate Selection Process | Recruiter View Configuration | Medium | FIT | Negative | 10 | 2 | 2 | Medium | Yes | No | Automate | 10 steps; 2 personas/1 logins; career-site/external UI; config/visibility assertion
78 | TC05-CE | REQ_CE_0006 | Candidate Experience | Application Flow (Easy Apply v3) | Medium | FIT | Positive | 14 | 2 | 4 | Medium | Yes | Yes | Automate | 14 steps; 2 personas/1 logins; career-site/external UI; file/doc handling; config/visibility assertion
79 | TC06-CE | REQ_CE_0007 | Candidate Experience | Application Question Sets | High | FIT | Positive | 12 | 1 | 3 | Medium | Yes | No | Automate | 12 steps; career-site/external UI
80 | TC07-CE | REQ_CE_0008 | Candidate Experience | Country-Specific Application Flows | Medium | FIT | Positive | 11 | 2 | 3 | Medium | Yes | Yes | Automate | 11 steps; 2 personas/1 logins; career-site/external UI
81 | TC08-CE | REQ_CE_0009 | Candidate Experience | Career Site Compliance Content | High | FIT | Positive | 9 | 1 | 2 | Medium | Yes | Yes | Automate | 9 steps; career-site/external UI
82 | TC09-CE | REQ_CE_0009 | Candidate Experience | Career Site Compliance Content | High | FIT | Negative | 10 | 1 | 2 | Medium | Yes | Yes | Automate | 10 steps; career-site/external UI
83 | TC03-CSP | REQ_CSP_0002 | Candidate Selection Process | Rehire Check Integration | Medium | FIT | Positive | 10 | 2 | 2 | Medium | Yes | No | Automate | 10 steps; 2 personas/1 logins
84 | TC020-REF | REQ_ERP_0014 | Employee Referral | Referral Consent / Compliance | High | FIT | Positive | 13 | 2 | 3 | Medium | Yes | No | Automate | 13 steps; 2 personas/1 logins
85 | TC021-REF | REQ_ERP_0014 | Employee Referral | Referral Consent / Compliance | High | FIT | Negative | 11 | 2 | 2 | Medium | Yes | No | Automate | 11 steps; 2 personas/1 logins
86 | TC026-JR | REQ_JR_0020 | Job Requisition | Prescreening Question Template | High | FIT | Positive | 13 | 2 | 4 | Medium | Yes | No | Automate | 13 steps; 2 personas/1 logins; career-site/external UI
87 | TC027-JR | REQ_JR_0020 | Job Requisition | Prescreening Question Template | High | FIT | Negative | 12 | 1 | 3 | Medium | Yes | No | Automate | 12 steps; career-site/external UI
88 | TC028-JR | REQ_JR_0021 | Job Requisition | Requisition Status (Custom) | Low | FIT | Positive | 11 | 2 | 2 | Medium | Yes | No | Automate | 11 steps; 2 personas/1 logins
89 | TC018-JO | REQ_JO_0017 | Job Offer | Offer Document Attachments | Medium | FIT | Positive | 12 | 2 | 5 | Complex | Yes | No | Automate | 12 steps; 2 personas/1 logins; email/notification; file/doc handling
90 | TC019-JO | REQ_JO_0018 | Job Offer | Compensation / Approval Matrix Automation | High | PARTIAL FIT | Positive | 12 | 2 | 5 | Complex | Yes | No | Automate | 12 steps; 2 personas/1 logins; approval workflow; file/doc handling
91 | TC020-JO | REQ_JO_0019 | Job Offer | Offer Fitment Form | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; approval workflow
92 | TC010-CE | REQ_CE_0010 | Candidate Experience | Candidate Profile Sharing | Medium | FIT | Positive | 12 | 3 | 4 | Medium | Yes | No | Automate | 12 steps; 3 personas/2 logins
93 | TC04-INT | REQ_ING_0004 | Integration | Talview Integration - Reporting | Medium | PARTIAL FIT | Positive | 11 | 2 | 6 | Complex | Yes | No | Automate (stub/mock 3rd party) | 11 steps; 2 personas/1 logins; 3rd-party integration; report/OTBI
94 | TC05-INT | REQ_ING_0005 | Integration | Talview Integration - Resume Flow | Medium | PARTIAL FIT | Positive | 12 | 1 | 7 | Complex | Yes | No | Automate (stub/mock 3rd party) | 12 steps; 1 personas/2 logins; 3rd-party integration; file/doc handling
95 | TC04-CSP | REQ_CSP_0003 | Candidate Selection Process | Candidate History Preservation | Medium | FIT | Positive | 11 | 1 | 2 | Medium | Yes | No | Automate | 11 steps; file/doc handling
96 | TC05-CSP | REQ_CSP_0004 | Candidate Selection Process | Bulk Candidate Search | Medium | FIT | Positive | 10 | 1 | 3 | Medium | Yes | No | Automate | 10 steps; email/notification; bulk/mass action
97 | TC06-CSP | REQ_CSP_0005 | Candidate Selection Process | Bulk Candidate Actions | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; bulk/mass action
98 | TC07-CSP | REQ_CSP_0006 | Candidate Selection Process | Candidate Status Labels | Medium | FIT | Positive | 12 | 2 | 2 | Medium | Yes | No | Automate | 12 steps; 2 personas/2 logins; config/visibility assertion
99 | TC021-JO | REQ_JO_0020 | Job Offer | Offer Phase States | Medium | FIT | Positive | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; approval workflow
100 | TC029-JR | REQ_JR_0022 | Job Requisition | System Status Labels | Medium | FIT | Positive | 11 | 3 | 3 | Medium | Yes | No | Automate | 11 steps; 3 personas/2 logins; report/OTBI; config/visibility assertion
101 | TC030-JR | REQ_JR_0022 | Job Requisition | System Status Labels | Medium | FIT | Negative | 10 | 3 | 2 | Medium | Yes | No | Automate | 10 steps; 3 personas/1 logins; config/visibility assertion
102 | TC08-CSP | REQ_CSP_0007 | Candidate Selection Process | Candidate Lifecycle Transfer | Medium | FIT | Positive | 12 | 1 | 3 | Medium | Yes | No | Automate | 12 steps; file/doc handling
103 | TC011-CE | REQ_CE_0011 | Candidate Experience | Career Site Import/Branding Reuse | Low | FIT | Positive | 12 | 2 | 3 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; career-site/external UI; config/visibility assertion
104 | TC012-CE | REQ_CE_0012 | Candidate Experience | AI Agent Reuse | Low | FIT | Positive | 12 | 2 | 7 | Complex | No | No | Manual (AI/non-deterministic) | 12 steps; 2 personas/1 logins; AI/non-deterministic; career-site/external UI
105 | TC06-INT | REQ_ING_0006 | Integration | Background Check Integration | High | FIT | Positive | 12 | 1 | 5 | Complex | Yes | No | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration
106 | TC09-CSP | REQ_CSP_0008 | Candidate Selection Process | Disposition Governance | Medium | FIT | Positive | 12 | 3 | 3 | Medium | Yes | No | Automate | 12 steps; 3 personas/4 logins; config/visibility assertion
107 | TC010-CSP | REQ_CSP_0008 | Candidate Selection Process | Disposition Governance | Medium | FIT | Negative | 11 | 1 | 0 | Simple | Yes | No | Automate | 11 steps; config/visibility assertion
108 | TC011-CSP | REQ_CSP_0009 | Candidate Selection Process | Recruiter vs HM Ownership | Medium | FIT | Positive | 12 | 3 | 3 | Medium | Yes | No | Automate | 12 steps; 3 personas/3 logins; config/visibility assertion
109 | TC012-CSP | REQ_CSP_0009 | Candidate Selection Process | Recruiter vs HM Ownership | Medium | FIT | Negative | 12 | 2 | 2 | Medium | Yes | No | Automate | 12 steps; 2 personas/2 logins; config/visibility assertion
110 | TC013-CSP | REQ_CSP_0010 | Candidate Selection Process | AI - JD to Questions | Medium | PARTIAL FIT | Positive | 11 | 1 | 2 | Medium | Yes | No | Automate | 11 steps; file/doc handling
111 | TC014-CSP | REQ_CSP_0011 | Candidate Selection Process | Contextualization Rules | Medium | FIT | Positive | 11 | 2 | 3 | Medium | Yes | Yes | Automate | 11 steps; 2 personas/1 logins; career-site/external UI
112 | TC015-CSP | REQ_CSP_0012 | Candidate Selection Process | Job Codes / Prescreening Updates | Medium | FIT | Positive | 12 | 3 | 5 | Complex | Yes | Yes | Automate | 12 steps; 3 personas/2 logins; career-site/external UI
113 | TC08-INTM | REQ_INTM_0007 | Interview Management | Candidate/HM Survey Framework | Medium | FIT | Positive | 12 | 2 | 3 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins
114 | TC09-INTM | REQ_INTM_0008 | Interview Management | Survey Reporting | Medium | PARTIAL FIT | Positive | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; report/OTBI
115 | TC031-JR | REQ_JR_0023 | Job Requisition | Agency Onboarding Governance | Medium | FIT | Positive | 10 | 4 | 4 | Medium | Yes | No | Automate | 10 steps; 4 personas/1 logins; approval workflow
116 | TC016-CSP | REQ_CSP_0013 | Candidate Selection Process | Duplicate Check Checkpoints | High | FIT | Positive | 12 | 2 | 3 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins
117 | TC017-CSP | REQ_CSP_0013 | Candidate Selection Process | Duplicate Check Checkpoints | High | FIT | Negative | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; email/notification
118 | TC018-CSP | REQ_CSP_0014 | Candidate Selection Process | Duplicate Match Logic | High | FIT | Positive | 12 | 2 | 4 | Medium | Yes | No | Automate | 12 steps; 2 personas/1 logins; email/notification
119 | TC019-CSP | REQ_CSP_0015 | Candidate Selection Process | Source Ownership Logic | High | FIT | Positive | 12 | 3 | 5 | Complex | Yes | No | Automate | 12 steps; 3 personas/1 logins; career-site/external UI
120 | TC020-CSP | REQ_CSP_0016 | Candidate Selection Process | Source Edit Access Control | Medium | FIT | Positive | 11 | 2 | 2 | Medium | Yes | No | Automate | 11 steps; 2 personas/2 logins
121 | TC021-CSP | REQ_CSP_0016 | Candidate Selection Process | Source Edit Access Control | Medium | FIT | Negative | 11 | 2 | 1 | Simple | Yes | No | Automate | 11 steps; 2 personas/1 logins; config/visibility assertion
122 | TC022-CSP | REQ_CSP_0017 | Candidate Selection Process | Source Taxonomy | Medium | PARTIAL FIT | Positive | 13 | 1 | 4 | Medium | Yes | No | Automate | 13 steps; email/notification; report/OTBI
123 | TC01-SEC | REQ_SEC_0001 | Security | Agency View Restriction | Medium | FIT | Positive | 10 | 2 | 1 | Simple | Yes | No | Automate | 10 steps; 2 personas/2 logins; config/visibility assertion
124 | TC02-SEC | REQ_SEC_0001 | Security | Agency View Restriction | Medium | FIT | Negative | 10 | 3 | 2 | Medium | Yes | No | Automate | 10 steps; 3 personas/2 logins; config/visibility assertion
125 | TC023-CSP | REQ_CSP_0018 | Candidate Selection Process | Source Ownership Retention | Medium | FIT | Positive | 11 | 2 | 1 | Simple | Yes | No | Automate | 11 steps; 2 personas/1 logins; config/visibility assertion
126 | TC01-AI | REQ_AI_0001 | AI Agents | AI Referral Matching | Medium | GAP | Positive | 11 | 2 | 4 | Medium | No | No | Manual (GAP - workaround only) | 11 steps; 2 personas/1 logins; career-site/external UI; file/doc handling
127 | TC07-INT | REQ_ING_0007 | Integration | Document Storage Integration | Medium | PARTIAL FIT | Positive | 12 | 1 | 6 | Complex | Yes | No | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration; file/doc handling
128 | TC08-INT | REQ_ING_0008 | Integration | Onboarding-PeopleSoft Integration | High | PARTIAL FIT | Positive | 13 | 2 | 6 | Complex | Yes | No | Automate (stub/mock 3rd party) | 13 steps; 2 personas/1 logins; 3rd-party integration
129 | TC09-INT | REQ_ING_0009 | Integration | Document Records - eStorage | Medium | PARTIAL FIT | Positive | 12 | 1 | 6 | Complex | Yes | No | Automate (stub/mock 3rd party) | 12 steps; 3rd-party integration; file/doc handling
130 | TC013-CE | REQ_CE_0013 | Candidate Experience | Duplicate/Prior Application Visibility | Medium | FIT | Positive | 12 | 1 | 2 | Medium | Yes | No | Automate | 12 steps
131 | TC03-SEC | REQ_SEC_0002 | Security | Country/Team Access Restriction | High | FIT | Positive | 11 | 0 | 1 | Simple | Yes | Yes | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
132 | TC04-SEC | REQ_SEC_0002 | Security | Country/Team Access Restriction | High | FIT | Negative | 11 | 2 | 1 | Simple | Yes | Yes | Automate | 11 steps; 2 personas/1 logins; config/visibility assertion
133 | TC01-RB | REQ_RB_0001 | Recruiting Booster | Targeted Campaigns | Medium | PARTIAL FIT | Positive | 12 | 1 | 3 | Medium | No | No | Manual (external channel) | 12 steps; email/notification
134 | TC024-CSP | REQ_CSP_0019 | Candidate Selection Process | Campus & Event Management | Medium | FIT | Positive | 12 | 2 | 7 | Complex | Yes | No | Automate | 12 steps; 2 personas/1 logins; 3rd-party integration; bulk/mass action
135 | TC02-RB | REQ_RB_0002 | Recruiting Booster | SMS Communication | Medium | GAP | Positive | 11 | 1 | 5 | Complex | No | No | Manual (GAP - workaround only) | 11 steps; 3rd-party integration; email/notification
136 | TC022-JO | REQ_JO_0021 | Job Offer | Salary Data Restriction | High | FIT | Positive | 11 | 0 | 1 | Simple | Yes | No | Automate | 11 steps; 1 personas/2 logins; config/visibility assertion
137 | TC023-JO | REQ_JO_0021 | Job Offer | Salary Data Restriction | High | FIT | Negative | 6 | 1 | -1 | Simple | Yes | No | Automate | 6 steps; config/visibility assertion
138 | TC01-REP | REQ_REP_0001 | Reporting & Analytics | Real-Time Metrics Dashboard | Medium | FIT | Positive | 6 | 2 | 2 | Medium | Yes | No | Automate | 6 steps; 2 personas/1 logins; report/OTBI
139 | TC02-AI | REQ_AI_0002 | AI Agents | Voice AI Agents | Medium | GAP | Positive | 6 | 2 | 4 | Medium | No | No | Manual (AI/non-deterministic) | 6 steps; 2 personas/1 logins; AI/non-deterministic
140 | TC032-JR | REQ_JR_0025 | Job Requisition | Recruiter-Owned Process Governance | Medium | FIT | Positive | 6 | 4 | 2 | Medium | Yes | No | Automate | 6 steps; 4 personas/3 logins
141 | TC05-SEC | REQ_SEC_0003 | Security | Interview/Selection/Offer Visibility | High | FIT | Positive | 6 | 2 | 1 | Simple | Yes | No | Automate | 6 steps; 2 personas/3 logins; config/visibility assertion
142 | TC03-AI | REQ_AI_0003 | AI Agents | AI in Candidate Selection Process | Medium | FIT | Positive | 6 | 3 | 2 | Medium | No | No | Manual (AI/non-deterministic) | 6 steps; 3 personas/1 logins
143 | TC02-REP | REQ_REP_0002 | Reporting & Analytics | Admin/MIS Report Restriction | Medium | FIT | Positive | 6 | 1 | 2 | Medium | Yes | No | Automate | 6 steps; 1 personas/3 logins; report/OTBI; config/visibility assertion
144 | TC03-REP | REQ_REP_0002 | Reporting & Analytics | Admin/MIS Report Restriction | Medium | FIT | Negative | 6 | 2 | 1 | Simple | Yes | No | Automate | 6 steps; 2 personas/1 logins; report/OTBI; config/visibility assertion
145 | TC06-SEC | REQ_SEC_0004 | Security | Role-Based Recruiter Assignment | High | FIT | Positive | 6 | 2 | 1 | Simple | Yes | Yes | Automate | 6 steps; 2 personas/1 logins
146 | TC07-SEC | REQ_SEC_0005 | Security | US Collaborator/Recruiter Restrictions | High | FIT | Positive | 6 | 2 | 1 | Simple | Yes | No | Automate | 6 steps; 2 personas/5 logins; config/visibility assertion
147 | TC08-SEC | REQ_SEC_0005 | Security | US Collaborator/Recruiter Restrictions | High | FIT | Positive | 12 | 3 | 4 | Medium | Yes | Yes | Automate | 12 steps; 3 personas/2 logins; approval workflow; config/visibility assertion
148 | TC09-SEC | REQ_SEC_0006 | Security | US Collaborator Offer Restriction | High | FIT | Negative | 12 | 2 | 3 | Medium | Yes | No | Automate | 12 steps; 2 personas/3 logins; config/visibility assertion
149 | TC024-JO | REQ_JO_0022 | Job Offer | Offer Proposal / Dynamic Approvals / Contract Generation | High | FIT | Positive | 13 | 4 | 6 | Complex | Yes | No | Automate | 13 steps; 4 personas/2 logins; approval workflow; file/doc handling
150 | TC025-JO | REQ_JO_0023 | Job Offer | Offer Document Library / Mandatory Attachments | High | FIT | Positive | 12 | 3 | 5 | Complex | Yes | No | Automate | 12 steps; 3 personas/1 logins; file/doc handling
151 | TC026-JO | REQ_JO_0024 | Job Offer | Offer Letter Compliance / Job Description & Designation | High | FIT | Positive | 12 | 1 | 3 | Medium | Yes | Yes | Automate | 12 steps; report/OTBI
152 | TC025-CSP | REQ_CSP_0020 | Candidate Selection Process | Rehire Employee ID Capture / Flow | High | FIT | Positive | 9 | 2 | 5 | Complex | Yes | No | Automate | 9 steps; 2 personas/1 logins; email/notification; report/OTBI; career-site/external UI

## Overall Estimation
TEST AUTOMATION ESTIMATE — ATS Oracle Recruiting Cloud (ORC), Phase 1
Approach: Selenium WebDriver + Cucumber BDD, extending the existing Oracle Fusion regression framework. ¦ Blue-on-yellow cells are inputs; everything else is formula-driven.
Effort Breakdown
| Activity | Description | Hours | Complexity | Volume | Rate | Basis
| Test Analysis / KT | Walkthrough of the Fit/Gap V1.1 recruiting processes; analysis of each script into Gherkin scenarios and reusable steps. | 22.9167 | Simple | 34 | 5 | 2.8333 | Minutes per script
|  |  |  | Medium | 89 | 10 | 14.8333
|  |  |  | Complex | 21 | 15 | 5.25
[5 empty] | 144 | Total in hrs | 22.9167
| Framework Extension & Environment Set-up | Extend the existing framework for ORC: new feature files, step-definition and page-object packages per recruiting module, ORC-specific wait/sync helpers, test-data workbook, ORC instance access and multi-persona test users. | 120 | 15 Days
| Script Development | Build each scenario: Gherkin steps, step definitions, page objects and locators, assertions and screenshot capture. | 1308.4444 | Simple | Medium | Complex
|  |  |  | 0.67 | 1.11 | 2 | Days per script
|  |  |  | 1.5 | 0.9 | 0.5 | Scripts per day
|  |  |  | 181.3333 | 791.1111 | 336 | Hours
[5 empty] | Total in hrs | 1308.4444
| Country Data Parameterisation | Parameterise the country-variant scripts so country behaviour is driven by data, then build and validate one data row per Phase 1 country. | 202.5 | Variant scripts | 27 | 2 | 54 | Hours per script / per row
|  |  |  | Country data rows | 297 | 0.5 | 148.5
[6 empty] | Total in hrs | 202.5
| Dry Run Execution | Execute every script-execution at least once: stabilise scripts, triage failures, fix locators and timing, confirm each country data row passes. | 602 | Simple | Medium | Complex
|  |  |  | 0.13 | 0.17 | 0.33 | Days per execution
|  |  |  | 8 | 6 | 3 | Executions per day
|  |  |  | 94 | 345.3333 | 162.6667 | Hours
[5 empty] | Total in hrs | 602
| Project Management | Automation lead time: planning, status reporting, governance, defect co-ordination with the functional team. | 112.7931 | 5% | of build effort
| Contingency | Locator rework against the Oracle Redwood UI, environment downtime, test-data resets and script stabilisation beyond first pass. | 236.8654 | 10% | of effort incl. PM
|  | Overall Effort (Hours) | 2605.5196
|  | Total Person Days | 325.6899 | 1 person day = 8 hrs
|  | Total Person Weeks | 65.138 | 1 person week = 5 days
|  | Total Person Months | 15.0434 | 1 month = 4.33 weeks
|  | Automation Engineers | 3 | See "Resourcing Scenarios" for 3, 4 and 5 engineers
|  | Duration (Weeks) | 21.7127 | 5.0145 | Months

## Resourcing Scenarios
RESOURCING SCENARIOS — Phase 1
Total effort is the same in every scenario. More engineers compress the calendar; they do not reduce the work.
SQUAD COMPOSITION
Role | 3 Engineers | 4 Engineers | 5 Engineers | Counts as build capacity?
Automation Test Lead | 0.5 | 1 | 1 | No
Senior Automation Engineer | 1 | 1 | 2 | Yes
Automation Engineer | 2 | 3 | 3 | Yes
Functional SME / BA (ORC) | 1 | 1 | 1 | No
Automation Engineers | 3 | 4 | 5 | Senior + Engineers
Total Squad Size | 4.5 | 6 | 7
DURATION
Scenario | Automation Engineers | Team Efficiency | Effective Capacity | Computed Duration (Weeks) | Planned Duration (Weeks) | Planned Duration (Months) | Notes
3 engineers | 3 | 100% | 3 | 21.7127 | 21.7127 | 5.0145 | Lowest co-ordination overhead. Longest calendar.
4 engineers | 4 | 97% | 3.88 | 16.7881 | 16.7881 | 3.8772 | Balanced. Two build streams sharing one page-object library.
5 engineers | 5 | 94% | 4.7 | 13.8591 | 13.8591 | 3.2007 | Fastest. Needs all five onboarded in week 1.
Total effort (person weeks) | 65.138
Serial floor (weeks) | 5 | Framework extension, KT and final sign-off cannot be parallelised — no scenario finishes sooner than this.

## Phase Plan
INDICATIVE PHASE PLAN — Phase 1 (4-engineer scenario, ~17 weeks)
Weeks are relative to automation kick-off, not calendar dates. Under the 3- and 5-engineer scenarios the plan stretches or compresses proportionally.
Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
Test analysis & KT on ORC recruiting processes
Framework extension, environment & test users
Script development — Job Requisition, Employee Referral, Security
Script development — Job Offer, Candidate Selection, Candidate Experience
Country data parameterisation (11 countries)
Dry run & script stabilisation
Suite sign-off, handover & user guide

## Assumptions & Risks
ASSUMPTIONS, EXCLUSIONS & RISKS
BASIS OF ESTIMATE
| Scope source | ATS_ORC_Test_Script_Register_20AUG26.xlsx — 152 scripts from ATS - ORC - Fit/Gap V1.1, prepared by Tejal Dalavi, 17-Aug-2026.
| Phase 1 country scope | 11 of 81 countries. Country count is an input cell on the "Scope" tab — change it to re-estimate a later phase.
| Automation approach | Selenium WebDriver 4.40 + Cucumber 7.33 + TestNG + Allure, extending the team's existing Oracle Fusion regression framework.
| Existing assets reused | Measured in the current repository: 691 locators and 83 delivered scenarios across Core HR and Security, plus the shared driver, wait/sync wrapper, Excel data reader, screenshot and Allure reporting layers.
| Productivity rates | Planning assumptions, not measured from timesheets. All are editable input cells on the "Overall Estimation" tab.
ASSUMPTIONS
1 | The 152 scripts are baselined and signed off before build starts. The register currently notes that test steps, preconditions, test data and expected results are still to be edited and reviewed.
2 | A stable ORC test instance is available for the full duration, with no mid-build re-implementation of recruiting configuration.
3 | Test users exist for every persona — Recruiter, Hiring Manager, Employee/Referrer, Candidate, Interviewer, Agency, Administrator — with non-expiring passwords.
4 | Configuration for all 11 Phase 1 countries is complete in the test instance before country parameterisation begins.
5 | Test data (requisitions, candidates, offers) can be created and reset repeatably for each country.
6 | One person day = 8 hours, one person week = 5 days, one month = 4.33 weeks.
7 | Effort covers build and dry run only. Regression execution cycles after handover are estimated separately.
8 | Third-party integration scripts (Talview, Mercer Belong, PeopleSoft, background check, e-storage) are automated against stubs or a vendor sandbox; if neither exists these 9 scripts move to manual.
9 | Scripts run serially on a single browser session per scenario, matching the current framework. Parallel execution is not assumed in the dry-run rates.
EXCLUSIONS
1 | Performance, load, security-penetration and accessibility testing.
2 | Manual SIT/UAT execution effort, and the 8 scripts listed as excluded on the "Scope" tab.
3 | Countries 12–81. Later phases re-use the same scripts and add data rows plus execution passes only.
4 | Post-handover regression execution and ongoing maintenance for Oracle quarterly updates.
5 | Automation of ORC configuration itself (Setup and Maintenance tasks).
6 | CI/CD pipeline build-out and parallel-execution infrastructure.
RISKS
| Risk | Impact | Mitigation
| Scripts are not yet baselined — the register flags steps, data and expected results as still under review. | Rework of built scripts; the single largest threat to the estimate. | Gate the build on signed-off scripts; automate the stable modules first.
| Oracle Fusion generates element IDs at runtime and ORC screens are moving to the Redwood UI. | Locator breakage and rework; hand-coded Selenium carries this cost directly. | Centralise locators in page objects, prefer stable business attributes over positional XPath, extend the existing sync helper for Redwood components.
| Oracle ships four quarterly updates a year against the ORC instance. | Suite drifts out of date; regression value decays without funded maintenance. | Agree a maintenance retainer at handover and run the suite against each update preview.
| Country configuration for all 11 countries may not be ready when parameterisation starts. | Blocks 27 country-variant scripts and 297 of the 414 dry-run executions. | Confirm country readiness as a phase gate; sequence countries so ready ones are parameterised first.
| Serial execution — one browser session per scenario, quit after each. | 414 executions each pay a browser launch and Oracle login; dry run is the second-largest line in the estimate. | Reuse the session across scenarios of the same persona, or introduce parallel execution — both outside this estimate.
| Third-party integration sandboxes may be unavailable. | 9 Complex scripts cannot be automated end to end. | Confirm sandbox availability before build; otherwise stub the boundary and assert only ORC-side behaviour.